## README
Project Portfolio Tracker — Excel Dashboard
Companion to the Excel + SQL portfolio project. Built on synthetic data.
Tabs in this workbook
Tab | What's there
Dashboard | Executive view: KPI cards, project health chart, budget burn, capacity.
Exec_OnePager | Print-ready 1-page summary you can attach to LinkedIn or email.
Data_Projects | Cleaned project list with computed % complete, % budget burned, health flag.
Data_Tasks | Task-level data with overdue flag.
Data_TimeEntries_Wk | Weekly hours per employee with capacity flag.
Data_Budget | Monthly budget vs. actual per project with variance.
How to refresh
1. Replace data in the Data_* tabs (paste from SQL output).
2. All formulas, KPIs, and charts on the Dashboard recalculate automatically.
3. Update the 'As of' date in cell B3 of the Dashboard tab.

## Data_Projects
project_id | project_name | client_name | project_manager | start_date | planned_end_date | actual_end_date | status | budget_amount | actual_amount | pct_complete | pct_budget_burned | health_flag | overrun
1 | ERP Implementation | Acme Co. | Ian Parker | 2025-09-03 | 2026-04-19 |  | On Hold | 60000 | 70571.26 | 12.5% | 117.6% | Over Budget | 10571.26
2 | CRM Migration | Initech | Fatima Brown | 2026-01-12 | 2026-05-27 |  | On Hold | 80000 | 61637.85 | 80.95% | 77.05% | On Track | -18362.15
3 | Cloud Cost Optimization | Globex Logistics | Carlos Garcia | 2025-11-25 | 2026-05-12 | 2026-06-08 | Completed | 300000 | 264230.08 | 33.33% | 88.08% | At Risk | -35769.92
4 | Cybersecurity Uplift | Acme Co. | Brystal Patel | 2025-10-12 | 2026-06-07 |  | In Progress | 400000 | 448485.6 | 3.704% | 112.1% | Over Budget | 48485.6
5 | Data Warehouse Rebuild | Northwind Health | Tara Cooper | 2025-05-26 | 2025-10-18 |  | In Progress | 60000 | 24832.96 | 30% | 41.39% | On Track | -35167.04
6 | Customer Portal Refresh | Initech | Ian Parker | 2025-11-02 | 2026-04-13 |  | On Hold | 400000 | 291217.72 | 80% | 72.8% | On Track | -108782.28
7 | Mobile App Launch | Acme Co. | (unassigned) | 2025-08-10 | 2026-07-27 |  | In Progress | 300000 | 145584.09 | 50% | 48.53% | On Track | -154415.91
8 | HR Systems Consolidation | Cyberdyne | Eli Nguyen | 2025-08-16 | 2026-02-19 |  | On Hold | 300000 | 135360.05 | 43.33% | 45.12% | On Track | -164639.95
9 | Compliance Remediation | Initech | Ian Parker | 2025-05-23 | 2026-03-08 |  | Cancelled | 120000 | 134103.24 | 5.556% | 111.8% | Over Budget | 14103.24
10 | Procurement Automation | Cyberdyne | Tara Cooper | 2025-10-03 | 2026-03-27 |  | In Progress | 60000 | 41299.68 | 62.96% | 68.83% | On Track | -18700.32
11 | Reporting Modernization | Acme Co. | Ian Parker | 2025-09-24 | 2026-02-05 |  | In Progress | 120000 | 104491.44 | 26.67% | 87.08% | At Risk | -15508.56
12 | Network Upgrade | Vandelay Imports | Brystal Patel | 2025-06-16 | 2025-11-03 |  | In Progress | 80000 | 37667.9 | 37.04% | 47.08% | On Track | -42332.1
13 | Onboarding Redesign | Pied Piper | Dana Lee | 2025-11-03 | 2026-06-14 |  | In Progress | 60000 | 26040.2 | 37.04% | 43.4% | On Track | -33959.8
14 | Inventory Visibility | Wonka Mfg | Tara Cooper | 2026-01-21 | 2026-09-05 |  | Cancelled | 250000 | 167929.01 | 60% | 67.17% | On Track | -82070.99
15 | Patient Scheduling Pilot | Umbrella Bio | Fatima Brown | 2025-10-21 | 2026-04-11 |  | Cancelled | 150000 | 172363.52 | 13.04% | 114.9% | Over Budget | 22363.52
16 | Field Service Rollout | Soylent Foods | Eli Nguyen | 2025-08-13 | 2026-01-13 |  | Cancelled | 400000 | 344175.23 | 16.67% | 86.04% | At Risk | -55824.77
17 | Marketing Ops Migration | Hooli | Brystal Patel | 2026-01-25 | 2026-05-27 |  | On Hold | 80000 | 58747.08 | 71.43% | 73.43% | On Track | -21252.92
18 | Vendor Risk Program | Wonka Mfg | Carlos Garcia | 2025-11-14 | 2026-07-21 |  | Not Started | 250000 | 204091.48 | 11.11% | 81.64% | At Risk | -45908.52
19 | Service Desk Re-platform | Globex Logistics | Fatima Brown | 2026-01-27 | 2027-01-07 |  | In Progress | 200000 | 95493.56 | 46.67% | 47.75% | On Track | -104506.44
20 | Quality Management Rollout | Vandelay Imports | Tara Cooper | 2025-07-22 | 2026-06-20 | 2026-06-28 | Completed | 60000 | 51048.6 | 17.65% | 85.08% | At Risk | -8951.4

## Data_Tasks
task_id | project_id | task_name | assignee | due_date | completed_date | status | estimated_hours | overdue_flag
1 | 1 | Hand-off integration | Quinn Lewis | 2026-02-26 |  | Open | 4 | Overdue
2 | 1 | Implement UAT plan | Sofia Young | 2025-10-07 |  | In Progress | 40 | Overdue
3 | 1 | Test stakeholder briefing | Owen Murphy | 2025-11-02 |  | In Progress | 80 | Overdue
4 | 1 | Deploy risk register | Dana Lee | 2025-11-16 |  | In Progress | 4 | Overdue
5 | 1 | Deploy requirements | Alex Johnson | 2026-02-19 |  | Open | 16 | Overdue
6 | 1 | Deploy integration | Vera Cox | 2026-03-26 |  | Open | 24 | Overdue
7 | 1 | Validate requirements | Hassan Davis | 2026-01-29 |  | In Progress | 4 | Overdue
8 | 1 | Validate requirements | Xavier Green | 2026-03-05 |  | Blocked | 40 | Overdue
9 | 1 | Implement requirements | Theo Allen | 2026-01-29 |  | Open | 16 | Overdue
10 | 1 | Draft risk register | Wendy Scott | 2026-04-01 |  | Blocked | 8 | Overdue
11 | 1 | Review training materials | Zoe Smith | 2026-03-03 |  | Open | 40 | Overdue
12 | 1 | Kickoff integration | Priya Clark | 2025-12-23 |  | Blocked | 80 | Overdue
13 | 1 | Train integration | Aiden Hill | 2025-10-21 |  | Blocked | 4 | Overdue
14 | 1 | Document test cases | Aiden Hill | 2025-10-25 |  | In Progress | 80 | Overdue
15 | 1 | Deploy integration | Sam Bell | 2026-02-28 | 2026-02-28 | Done | 4
16 | 1 | Test reports | Diana Roberts | 2025-12-16 | 2025-12-24 | Done | 16
17 | 1 | Test requirements | Quincy Rogers | 2025-11-27 | 2025-11-27 | Done | 8
18 | 1 | Pilot data model | Zoe Smith | 2025-12-21 |  | Open | 16 | Overdue
19 | 1 | Configure stakeholder briefing | Ian Parker | 2025-12-08 |  | In Progress | 16 | Overdue
20 | 1 | Deploy integration | Lena Reyes | 2025-09-17 |  | Open | 16 | Overdue
21 | 1 | Configure training materials | Umar Bailey | 2025-09-19 |  | Open | 80 | Overdue
22 | 1 | Validate data model | Yara Baker | 2025-11-29 |  | Open | 40 | Overdue
23 | 1 | Kickoff rollout plan | Alex Johnson | 2025-10-28 |  | Open | 40 | Overdue
24 | 1 | Kickoff vendor SOW | Vera Cox | 2026-04-04 |  | In Progress | 60 | Overdue
25 | 2 | Approve training materials | Quincy Rogers | 2026-04-22 | 2026-04-25 | Done | 80
26 | 2 | Validate UAT plan | Quincy Rogers | 2026-02-19 | 2026-02-21 | Done | 24
27 | 2 | Validate integration | Maya Jackson | 2026-04-12 | 2026-04-14 | Done | 24
28 | 2 | Approve change request | Theo Allen | 2026-04-26 | 2026-04-24 | Done | 24
29 | 2 | Configure test cases | Lena Reyes | 2026-01-19 | 2026-01-18 | Done | 40
30 | 2 | Plan reports | Gavin Turner | 2026-04-11 | 2026-04-18 | Done | 24
31 | 2 | Validate stakeholder briefing | Owen Murphy | 2026-03-03 | 2026-03-05 | Done | 40
32 | 2 | Train reports | Rachel Morgan | 2026-04-14 |  | Open | 16 | Overdue
33 | 2 | Draft requirements | Priya Clark | 2026-03-17 | 2026-03-14 | Done | 24
34 | 2 | Kickoff vendor SOW | Yara Baker | 2026-02-06 | 2026-02-05 | Done | 24
35 | 2 | Plan vendor SOW | Alex Johnson | 2026-05-01 |  | In Progress | 80 | Overdue
36 | 2 | Implement test cases | Sam Bell | 2026-02-15 | 2026-02-15 | Done | 40
37 | 2 | Test risk register | Hassan Davis | 2026-05-17 |  | Open | 24
38 | 2 | Validate change request | Uma King | 2026-02-22 | 2026-03-03 | Done | 80
39 | 2 | Configure RACI | Jade Edwards | 2026-05-12 | 2026-05-21 | Done | 24
40 | 2 | Migrate UAT plan | Will Howard | 2026-02-28 | 2026-03-08 | Done | 8
41 | 2 | Migrate stakeholder briefing | Priya Clark | 2026-03-30 | 2026-04-08 | Done | 16
42 | 2 | Deploy reports | Ravi Walker | 2026-05-11 |  | Open | 16
43 | 2 | Implement integration | Olivia Harris | 2026-04-10 | 2026-04-05 | Done | 24
44 | 2 | Configure rollout plan | Victor Wright | 2026-02-27 | 2026-02-22 | Done | 40
45 | 2 | Pilot rollout plan | Yara Baker | 2026-05-18 | 2026-05-17 | Done | 80
46 | 3 | Draft training materials | Theo Allen | 2026-04-28 |  | Open | 80 | Overdue
47 | 3 | Validate vendor SOW | Vera Cox | 2026-03-11 | 2026-03-17 | Done | 40
48 | 3 | Test UAT plan | Bella Mitchell | 2026-05-05 | 2026-05-13 | Done | 24
49 | 3 | Plan stakeholder briefing | Zane Adams | 2025-12-09 |  | Open | 60 | Overdue
50 | 3 | Approve cutover | Brystal Patel | 2026-01-13 | 2026-01-10 | Done | 24
51 | 3 | Draft data model | Paige Cook | 2026-05-02 |  | In Progress | 24
52 | 3 | Draft UAT plan | Yara Baker | 2026-01-05 | 2026-01-03 | Done | 16
53 | 3 | Document test cases | Yara Baker | 2026-01-25 |  | In Progress | 16 | Overdue
54 | 3 | Review security review | Brystal Patel | 2026-03-19 |  | Open | 60 | Overdue
55 | 3 | Document reports | Paige Cook | 2026-04-19 |  | Open | 4 | Overdue
56 | 3 | Test RACI | Brystal Patel | 2025-12-12 | 2025-12-12 | Done | 40
57 | 3 | Migrate stakeholder briefing | Hassan Davis | 2026-01-10 |  | Open | 40 | Overdue
58 | 3 | Deploy test cases | Xavier Green | 2026-01-26 |  | In Progress | 8 | Overdue
59 | 3 | Kickoff vendor SOW | Hassan Davis | 2026-05-06 |  | In Progress | 80
60 | 3 | Review change request | Brystal Patel | 2026-01-12 |  | Blocked | 16 | Overdue
61 | 4 | Test data model | Lena Reyes | 2026-01-28 |  | Blocked | 60 | Overdue
62 | 4 | Review vendor SOW | Zoe Smith | 2026-05-19 |  | In Progress | 16
63 | 4 | Train data model | Kyle Collins | 2026-05-24 |  | In Progress | 80
64 | 4 | Configure stakeholder briefing | Xavier Green | 2025-10-29 |  | Open | 4 | Overdue
65 | 4 | Draft RACI | Aiden Hill | 2026-02-25 |  | In Progress | 80 | Overdue
66 | 4 | Document stakeholder briefing | Diana Roberts | 2026-02-21 |  | Open | 60 | Overdue
67 | 4 | Kickoff cutover | Paige Cook | 2025-11-27 |  | Open | 16 | Overdue
68 | 4 | Train security review | Diana Roberts | 2026-03-25 | 2026-04-04 | Done | 24
69 | 4 | Deploy training materials | Priya Clark | 2026-05-18 |  | In Progress | 80
70 | 4 | Migrate reports | Will Howard | 2025-11-10 |  | Open | 24 | Overdue
71 | 4 | Configure training materials | Brystal Patel | 2026-03-13 |  | In Progress | 24 | Overdue
72 | 4 | Migrate reports | Wendy Scott | 2026-05-24 |  | Open | 80
73 | 4 | Hand-off change request | Sam Bell | 2025-12-24 |  | Open | 16 | Overdue
74 | 4 | Test data model | Priya Clark | 2026-03-10 |  | Open | 60 | Overdue
75 | 4 | Train reports | Sam Bell | 2026-01-31 |  | Open | 24 | Overdue
76 | 4 | Migrate test cases | Brystal Patel | 2026-04-02 |  | In Progress | 4 | Overdue
77 | 4 | Kickoff reports | Theo Allen | 2026-01-02 |  | Open | 60 | Overdue
78 | 4 | Validate cutover | Wendy Scott | 2026-03-16 |  | Open | 24 | Overdue
79 | 4 | Document vendor SOW | Diana Roberts | 2026-04-27 |  | In Progress | 16 | Overdue
80 | 4 | Review vendor SOW | Maya Jackson | 2026-01-05 |  | Open | 16 | Overdue
81 | 4 | Train vendor SOW | Liam Thomas | 2025-11-18 |  | In Progress | 8 | Overdue
82 | 4 | Deploy vendor SOW | Lena Reyes | 2025-12-13 |  | In Progress | 80 | Overdue
83 | 4 | Review RACI | Maya Jackson | 2026-03-02 |  | In Progress | 16 | Overdue
84 | 4 | Deploy requirements | Tara Cooper | 2025-12-16 |  | Open | 40 | Overdue
85 | 4 | Draft cutover | Sofia Young | 2025-11-20 |  | Open | 60 | Overdue
86 | 4 | Train security review | Grace Khan | 2025-11-20 |  | In Progress | 80 | Overdue
87 | 4 | Migrate security review | Caleb Carter | 2025-10-22 |  | In Progress | 16 | Overdue
88 | 5 | Pilot security review | Hassan Davis | 2025-06-15 |  | In Progress | 80 | Overdue
89 | 5 | Review change request | Owen Murphy | 2025-06-18 |  | In Progress | 60 | Overdue
90 | 5 | Train change request | Theo Allen | 2025-06-15 |  | Open | 4 | Overdue
91 | 5 | Train rollout plan | Marcus Stewart | 2025-08-04 |  | Open | 40 | Overdue
92 | 5 | Migrate risk register | Caleb Carter | 2025-07-29 | 2025-08-03 | Done | 16
93 | 5 | Approve requirements | Nina Morris | 2025-09-19 |  | In Progress | 60 | Overdue
94 | 5 | Plan reports | Quinn Lewis | 2025-06-27 | 2025-06-26 | Done | 60
95 | 5 | Implement cutover | Eli Nguyen | 2025-06-22 |  | Open | 8 | Overdue
96 | 5 | Kickoff change request | Ethan Phillips | 2025-06-02 |  | In Progress | 16 | Overdue
97 | 5 | Kickoff UAT plan | Sam Bell | 2025-06-10 |  | Open | 80 | Overdue
98 | 5 | Test risk register | Quinn Lewis | 2025-09-26 |  | Open | 80 | Overdue
99 | 5 | Validate reports | Paige Cook | 2025-07-22 |  | In Progress | 8 | Overdue
100 | 5 | Draft integration | Theo Allen | 2025-08-09 | 2025-08-04 | Done | 40
101 | 5 | Migrate vendor SOW | Theo Allen | 2025-08-14 |  | In Progress | 60 | Overdue
102 | 5 | Validate security review | Caleb Carter | 2025-09-13 | 2025-09-22 | Done | 4
103 | 5 | Approve UAT plan | Brystal Patel | 2025-06-12 | 2025-06-15 | Done | 4
104 | 5 | Pilot RACI | Kyle Collins | 2025-07-30 |  | Blocked | 40 | Overdue
105 | 5 | Plan RACI | Ravi Walker | 2025-06-07 |  | Blocked | 40 | Overdue
106 | 5 | Migrate cutover | Paige Cook | 2025-06-12 | 2025-06-10 | Done | 24
107 | 5 | Approve rollout plan | Owen Murphy | 2025-08-12 |  | Open | 80 | Overdue
108 | 6 | Document training materials | Quincy Rogers | 2025-12-02 | 2025-12-08 | Done | 4
109 | 6 | Deploy stakeholder briefing | Zane Adams | 2025-12-20 | 2025-12-28 | Done | 80
110 | 6 | Review training materials | Quinn Lewis | 2026-03-29 |  | Open | 16 | Overdue
111 | 6 | Configure RACI | Gavin Turner | 2025-12-08 |  | Blocked | 80 | Overdue
112 | 6 | Migrate rollout plan | Dana Lee | 2025-11-09 | 2025-11-19 | Done | 8
113 | 6 | Plan security review | Will Howard | 2026-03-21 | 2026-03-29 | Done | 4
114 | 6 | Hand-off UAT plan | Caleb Carter | 2025-12-31 | 2025-12-28 | Done | 60
115 | 6 | Plan change request | Priya Clark | 2026-03-13 |  | Open | 60 | Overdue
116 | 6 | Validate rollout plan | Fatima Brown | 2025-12-19 | 2025-12-12 | Done | 8
117 | 6 | Plan RACI | Jorge Wilson | 2025-12-08 | 2025-12-04 | Done | 24
118 | 6 | Configure RACI | Ethan Phillips | 2026-01-22 | 2026-01-23 | Done | 24
119 | 6 | Configure reports | Marcus Stewart | 2026-01-10 | 2026-01-07 | Done | 40
120 | 6 | Train test cases | Aiden Hill | 2025-12-13 | 2025-12-14 | Done | 16
121 | 6 | Deploy vendor SOW | Theo Allen | 2026-03-18 | 2026-03-11 | Done | 80
122 | 6 | Pilot integration | Caleb Carter | 2026-04-08 | 2026-04-16 | Done | 40
123 | 6 | Train cutover | Yara Baker | 2026-03-12 | 2026-03-22 | Done | 24
124 | 6 | Approve rollout plan | Olivia Harris | 2026-01-30 | 2026-01-30 | Done | 80
125 | 6 | Kickoff security review | Tara Cooper | 2026-02-22 |  | Open | 80 | Overdue
126 | 6 | Migrate requirements | Imani Martin | 2026-02-14 | 2026-02-11 | Done | 40
127 | 6 | Pilot RACI | Caleb Carter | 2026-04-09 | 2026-04-05 | Done | 4
128 | 6 | Kickoff integration | Aiden Hill | 2026-03-23 | 2026-03-16 | Done | 80
129 | 6 | Train UAT plan | Victor Wright | 2025-12-18 |  | Open | 40 | Overdue
130 | 6 | Pilot stakeholder briefing | Ian Parker | 2026-02-18 | 2026-02-21 | Done | 24
131 | 6 | Pilot cutover | Carlos Garcia | 2026-01-29 | 2026-02-06 | Done | 40
132 | 6 | Plan risk register | Sofia Young | 2025-11-26 |  | In Progress | 8 | Overdue
133 | 6 | Train stakeholder briefing | Tara Cooper | 2025-12-02 | 2025-11-28 | Done | 80
134 | 6 | Hand-off requirements | Carlos Garcia | 2025-12-04 | 2025-12-06 | Done | 16
135 | 6 | Configure integration | Priya Clark | 2025-11-23 | 2025-11-27 | Done | 40
136 | 6 | Implement integration | Fatima Brown | 2026-02-22 | 2026-02-20 | Done | 40
137 | 6 | Migrate risk register | Lena Reyes | 2026-02-14 | 2026-02-14 | Done | 8
138 | 7 | Deploy stakeholder briefing | Alex Johnson | 2026-04-10 | 2026-04-17 | Done | 80
139 | 7 | Implement data model | Caleb Carter | 2026-04-12 | 2026-04-22 | Done | 16
140 | 7 | Configure vendor SOW | Quinn Lewis | 2026-06-13 |  | In Progress | 24
141 | 7 | Configure RACI | Ethan Phillips | 2026-01-18 |  | Open | 4 | Overdue
142 | 7 | Document change request | Sofia Young | 2025-12-16 |  | In Progress | 60 | Overdue
143 | 7 | Pilot stakeholder briefing | Zane Adams | 2026-01-15 |  | Open | 16 | Overdue
144 | 7 | Hand-off change request | Vera Cox | 2025-08-21 | 2025-08-15 | Done | 24
145 | 7 | Approve test cases | Wendy Scott | 2026-01-10 | 2026-01-10 | Done | 8
146 | 7 | Deploy stakeholder briefing | Will Howard | 2026-07-08 |  | Open | 60
147 | 7 | Plan data model | Owen Murphy | 2026-07-20 | 2026-07-17 | Done | 60
148 | 7 | Migrate requirements | Lena Reyes | 2025-09-06 |  | In Progress | 16 | Overdue
149 | 7 | Deploy training materials | Vera Cox | 2025-10-23 |  | Open | 24 | Overdue
150 | 7 | Train cutover | Xavier Green | 2025-11-14 |  | Open | 40 | Overdue
151 | 7 | Deploy risk register | Ethan Phillips | 2026-04-30 | 2026-04-28 | Done | 80
152 | 7 | Train data model | Diana Roberts | 2026-01-15 | 2026-01-18 | Done | 4
153 | 7 | Pilot stakeholder briefing | Umar Bailey | 2025-10-28 | 2025-10-28 | Done | 60
154 | 7 | Train cutover | Xavier Green | 2026-03-08 |  | Blocked | 4 | Overdue
155 | 7 | Validate data model | Diana Roberts | 2026-03-07 |  | Open | 16 | Overdue
156 | 7 | Approve rollout plan | Owen Murphy | 2026-07-27 | 2026-07-28 | Done | 16
157 | 7 | Draft change request | Jade Edwards | 2025-10-11 | 2025-10-19 | Done | 16
158 | 7 | Review stakeholder briefing | Diana Roberts | 2026-06-25 |  | Open | 60
159 | 7 | Implement requirements | Carlos Garcia | 2026-01-18 | 2026-01-14 | Done | 16
160 | 8 | Hand-off cutover | Imani Martin | 2025-09-21 |  | Open | 24 | Overdue
161 | 8 | Kickoff vendor SOW | Ian Parker | 2025-12-17 |  | In Progress | 24 | Overdue
162 | 8 | Hand-off rollout plan | Paige Cook | 2026-01-20 | 2026-01-17 | Done | 4
163 | 8 | Draft vendor SOW | Xavier Green | 2025-12-26 | 2025-12-27 | Done | 8
164 | 8 | Test RACI | Xavier Green | 2025-12-14 |  | In Progress | 4 | Overdue
165 | 8 | Hand-off stakeholder briefing | Wendy Scott | 2026-02-14 |  | In Progress | 4 | Overdue
166 | 8 | Review RACI | Diana Roberts | 2025-12-02 |  | In Progress | 4 | Overdue
167 | 8 | Plan change request | Brystal Patel | 2026-02-08 |  | Open | 4 | Overdue
168 | 8 | Implement test cases | Kyle Collins | 2025-11-16 |  | Open | 8 | Overdue
169 | 8 | Test change request | Noah White | 2025-09-09 | 2025-09-19 | Done | 80
170 | 8 | Implement test cases | Marcus Stewart | 2025-10-21 |  | In Progress | 4 | Overdue
171 | 8 | Implement cutover | Quinn Lewis | 2025-11-01 | 2025-10-29 | Done | 80
172 | 8 | Pilot requirements | Imani Martin | 2025-10-06 |  | Open | 4 | Overdue
173 | 8 | Approve training materials | Brystal Patel | 2025-11-22 | 2025-11-22 | Done | 8
174 | 8 | Kickoff rollout plan | Hailey Diaz | 2025-10-29 |  | Open | 4 | Overdue
175 | 8 | Train training materials | Gavin Turner | 2025-09-08 |  | In Progress | 40 | Overdue
176 | 8 | Test change request | Carlos Garcia | 2025-09-19 |  | In Progress | 60 | Overdue
177 | 8 | Plan requirements | Dana Lee | 2026-02-07 | 2026-02-14 | Done | 24
178 | 8 | Review security review | Tara Cooper | 2025-12-03 |  | In Progress | 24 | Overdue
179 | 8 | Approve integration | Eli Nguyen | 2025-09-10 | 2025-09-13 | Done | 8
180 | 8 | Kickoff training materials | Yara Baker | 2025-11-01 | 2025-11-11 | Done | 40
181 | 8 | Validate change request | Bella Mitchell | 2026-01-05 |  | In Progress | 4 | Overdue
182 | 8 | Plan stakeholder briefing | Zoe Smith | 2026-02-18 |  | Open | 40 | Overdue
183 | 8 | Hand-off reports | Aiden Hill | 2025-10-17 |  | In Progress | 16 | Overdue
184 | 8 | Kickoff data model | Uma King | 2025-12-17 |  | In Progress | 24 | Overdue
185 | 8 | Implement stakeholder briefing | Ethan Phillips | 2025-11-11 | 2025-11-15 | Done | 4
186 | 8 | Configure data model | Vera Cox | 2025-09-15 | 2025-09-10 | Done | 60
187 | 8 | Draft change request | Jade Edwards | 2025-11-26 | 2025-12-06 | Done | 40
188 | 8 | Document RACI | Quincy Rogers | 2025-11-15 | 2025-11-21 | Done | 80
189 | 8 | Deploy change request | Theo Allen | 2025-12-09 | 2025-12-03 | Done | 16
190 | 9 | Plan security review | Olivia Harris | 2026-02-13 |  | Open | 80 | Overdue
191 | 9 | Validate training materials | Hassan Davis | 2025-07-24 |  | Open | 80 | Overdue
192 | 9 | Train rollout plan | Jade Edwards | 2025-10-19 |  | In Progress | 80 | Overdue
193 | 9 | Plan RACI | Sam Bell | 2025-06-12 |  | In Progress | 16 | Overdue
194 | 9 | Kickoff test cases | Theo Allen | 2025-06-13 |  | Open | 16 | Overdue
195 | 9 | Pilot integration | Kyle Collins | 2025-11-25 |  | Open | 60 | Overdue
196 | 9 | Kickoff stakeholder briefing | Brystal Patel | 2025-12-21 |  | Open | 4 | Overdue
197 | 9 | Configure security review | Victor Wright | 2026-02-25 |  | Open | 8 | Overdue
198 | 9 | Document test cases | Kyle Collins | 2025-12-05 |  | Open | 40 | Overdue
199 | 9 | Implement test cases | Nina Morris | 2025-07-12 | 2025-07-09 | Done | 4
200 | 9 | Plan rollout plan | Fiona Evans | 2025-07-10 |  | Open | 40 | Overdue
201 | 9 | Test test cases | Gavin Turner | 2026-01-11 |  | Open | 4 | Overdue
202 | 9 | Deploy stakeholder briefing | Rachel Morgan | 2025-11-22 |  | Open | 40 | Overdue
203 | 9 | Deploy requirements | Olivia Harris | 2026-02-03 |  | In Progress | 24 | Overdue
204 | 9 | Deploy reports | Zoe Smith | 2025-06-27 |  | Open | 8 | Overdue
205 | 9 | Review requirements | Fiona Evans | 2025-10-07 |  | Open | 60 | Overdue
206 | 9 | Configure cutover | Tara Cooper | 2026-01-05 |  | Open | 8 | Overdue
207 | 9 | Plan test cases | Wendy Scott | 2026-02-10 |  | In Progress | 4 | Overdue
208 | 10 | Hand-off data model | Uma King | 2025-10-20 | 2025-10-27 | Done | 40
209 | 10 | Deploy data model | Zane Adams | 2026-01-27 | 2026-02-02 | Done | 4
210 | 10 | Approve security review | Sam Bell | 2026-01-01 |  | Open | 16 | Overdue
211 | 10 | Test rollout plan | Lena Reyes | 2025-11-01 | 2025-10-28 | Done | 24
212 | 10 | Pilot UAT plan | Vera Cox | 2026-02-21 |  | Open | 16 | Overdue
213 | 10 | Review cutover | Owen Murphy | 2025-12-05 | 2025-12-03 | Done | 4
214 | 10 | Document vendor SOW | Paige Cook | 2026-02-22 | 2026-02-26 | Done | 80
215 | 10 | Implement UAT plan | Maya Jackson | 2025-11-16 |  | In Progress | 8 | Overdue
216 | 10 | Train stakeholder briefing | Eli Nguyen | 2026-03-13 |  | Open | 8 | Overdue
217 | 10 | Plan risk register | Kyle Collins | 2026-03-19 | 2026-03-26 | Done | 60
218 | 10 | Document RACI | Owen Murphy | 2026-03-21 |  | Blocked | 16 | Overdue
219 | 10 | Migrate stakeholder briefing | Theo Allen | 2025-11-17 | 2025-11-25 | Done | 80
220 | 10 | Validate data model | Theo Allen | 2025-12-19 | 2025-12-23 | Done | 24
221 | 10 | Document RACI | Sofia Young | 2026-02-02 |  | Open | 4 | Overdue
222 | 10 | Approve change request | Gavin Turner | 2026-03-24 | 2026-03-19 | Done | 24
223 | 10 | Migrate risk register | Kyle Collins | 2026-02-05 | 2026-01-30 | Done | 60
224 | 10 | Validate integration | Dana Lee | 2025-11-27 | 2025-12-05 | Done | 24
225 | 10 | Kickoff data model | Gavin Turner | 2025-11-05 | 2025-11-08 | Done | 60
226 | 10 | Kickoff security review | Caleb Carter | 2025-11-23 |  | Open | 40 | Overdue
227 | 10 | Document risk register | Sofia Young | 2026-02-20 | 2026-02-24 | Done | 24
228 | 10 | Train stakeholder briefing | Paige Cook | 2026-01-22 | 2026-01-16 | Done | 16
229 | 10 | Plan rollout plan | Sofia Young | 2025-10-26 | 2025-11-05 | Done | 16
230 | 10 | Approve RACI | Jorge Wilson | 2026-03-27 |  | Blocked | 16 | Overdue
231 | 10 | Hand-off training materials | Theo Allen | 2025-10-30 | 2025-10-27 | Done | 60
232 | 10 | Kickoff data model | Theo Allen | 2026-01-18 |  | Open | 40 | Overdue
233 | 10 | Pilot integration | Quincy Rogers | 2026-01-14 | 2026-01-17 | Done | 60
234 | 10 | Plan rollout plan | Gavin Turner | 2026-02-21 |  | Open | 16 | Overdue
235 | 11 | Test training materials | Zoe Smith | 2026-01-01 |  | Open | 24 | Overdue
236 | 11 | Implement integration | Eli Nguyen | 2025-11-19 |  | Open | 16 | Overdue
237 | 11 | Validate RACI | Vera Cox | 2025-10-26 |  | In Progress | 40 | Overdue
238 | 11 | Hand-off test cases | Nina Morris | 2025-10-10 |  | In Progress | 8 | Overdue
239 | 11 | Implement RACI | Sam Bell | 2026-01-05 |  | Open | 80 | Overdue
240 | 11 | Draft rollout plan | Xavier Green | 2025-11-12 |  | In Progress | 60 | Overdue
241 | 11 | Approve UAT plan | Will Howard | 2025-11-30 |  | Blocked | 60 | Overdue
242 | 11 | Test UAT plan | Ethan Phillips | 2026-01-23 |  | Open | 80 | Overdue
243 | 11 | Approve security review | Diana Roberts | 2025-11-19 |  | Open | 80 | Overdue
244 | 11 | Validate rollout plan | Kelly Anderson | 2025-12-12 | 2025-12-21 | Done | 80
245 | 11 | Pilot UAT plan | Dana Lee | 2025-11-21 | 2025-11-18 | Done | 60
246 | 11 | Hand-off data model | Tara Cooper | 2026-02-01 | 2026-02-11 | Done | 80
247 | 11 | Train integration | Ravi Walker | 2025-11-01 |  | Open | 24 | Overdue
248 | 11 | Hand-off reports | Caleb Carter | 2025-11-07 | 2025-11-02 | Done | 16
249 | 11 | Configure cutover | Xavier Green | 2025-10-07 |  | In Progress | 8 | Overdue
250 | 12 | Draft training materials | Grace Khan | 2025-07-13 |  | In Progress | 80 | Overdue
251 | 12 | Draft UAT plan | Ethan Phillips | 2025-09-16 | 2025-09-13 | Done | 60
252 | 12 | Migrate change request | Alex Johnson | 2025-07-28 | 2025-08-05 | Done | 4
253 | 12 | Pilot integration | Jade Edwards | 2025-06-27 |  | In Progress | 60 | Overdue
254 | 12 | Deploy reports | Theo Allen | 2025-10-09 |  | Open | 4 | Overdue
255 | 12 | Plan test cases | Nina Morris | 2025-07-05 |  | Open | 24 | Overdue
256 | 12 | Hand-off security review | Marcus Stewart | 2025-07-09 |  | Open | 40 | Overdue
257 | 12 | Kickoff integration | Sofia Young | 2025-06-27 | 2025-06-27 | Done | 24
258 | 12 | Approve rollout plan | Liam Thomas | 2025-06-23 | 2025-06-23 | Done | 60
259 | 12 | Review cutover | Ian Parker | 2025-07-14 | 2025-07-18 | Done | 40
260 | 12 | Pilot security review | Carlos Garcia | 2025-10-30 | 2025-11-04 | Done | 60
261 | 12 | Deploy vendor SOW | Brystal Patel | 2025-09-30 |  | Blocked | 16 | Overdue
262 | 12 | Kickoff stakeholder briefing | Owen Murphy | 2025-07-10 |  | In Progress | 4 | Overdue
263 | 12 | Document cutover | Victor Wright | 2025-09-16 |  | Open | 80 | Overdue
264 | 12 | Kickoff security review | Owen Murphy | 2025-08-06 | 2025-08-13 | Done | 8
265 | 12 | Train security review | Carlos Garcia | 2025-07-27 |  | Open | 16 | Overdue
266 | 12 | Test risk register | Carlos Garcia | 2025-08-13 |  | Open | 16 | Overdue
267 | 12 | Migrate UAT plan | Carlos Garcia | 2025-09-10 | 2025-09-20 | Done | 80
268 | 12 | Pilot test cases | Dana Lee | 2025-08-10 |  | In Progress | 80 | Overdue
269 | 12 | Train training materials | Bella Mitchell | 2025-09-15 |  | In Progress | 24 | Overdue
270 | 12 | Document integration | Fiona Evans | 2025-10-13 | 2025-10-18 | Done | 60
271 | 12 | Train cutover | Ravi Walker | 2025-10-28 |  | In Progress | 80 | Overdue
272 | 12 | Configure change request | Liam Thomas | 2025-07-14 | 2025-07-09 | Done | 40
273 | 12 | Review training materials | Quincy Rogers | 2025-09-06 |  | In Progress | 16 | Overdue
274 | 12 | Kickoff rollout plan | Kelly Anderson | 2025-09-09 |  | In Progress | 60 | Overdue
275 | 12 | Draft vendor SOW | Wendy Scott | 2025-10-14 |  | In Progress | 40 | Overdue
276 | 12 | Train requirements | Eli Nguyen | 2025-10-12 |  | In Progress | 60 | Overdue
277 | 13 | Draft integration | Marcus Stewart | 2026-02-11 | 2026-02-09 | Done | 60
278 | 13 | Implement data model | Priya Clark | 2026-05-29 |  | In Progress | 80
279 | 13 | Configure change request | Carlos Garcia | 2026-04-24 |  | In Progress | 40 | Overdue
280 | 13 | Document security review | Will Howard | 2025-12-19 | 2025-12-23 | Done | 4
281 | 13 | Document rollout plan | Uma King | 2026-04-05 |  | Open | 60 | Overdue
282 | 13 | Review requirements | Vera Cox | 2026-01-20 |  | Open | 8 | Overdue
283 | 13 | Review UAT plan | Zoe Smith | 2026-03-17 | 2026-03-27 | Done | 16
284 | 13 | Approve UAT plan | Sam Bell | 2026-05-09 |  | In Progress | 24
285 | 13 | Pilot data model | Caleb Carter | 2025-12-31 |  | Open | 8 | Overdue
286 | 13 | Review test cases | Rachel Morgan | 2026-05-11 |  | In Progress | 80
287 | 13 | Validate cutover | Sofia Young | 2026-01-30 | 2026-01-25 | Done | 16
288 | 13 | Train training materials | Gavin Turner | 2025-12-20 | 2025-12-18 | Done | 8
289 | 13 | Train integration | Priya Clark | 2025-12-11 |  | Blocked | 80 | Overdue
290 | 13 | Validate change request | Xavier Green | 2026-03-16 |  | Open | 24 | Overdue
291 | 13 | Implement change request | Fatima Brown | 2026-06-03 |  | Blocked | 4
292 | 13 | Kickoff vendor SOW | Ethan Phillips | 2026-01-28 |  | In Progress | 40 | Overdue
293 | 13 | Implement training materials | Paige Cook | 2026-02-23 | 2026-02-18 | Done | 4
294 | 13 | Validate training materials | Imani Martin | 2026-03-05 |  | In Progress | 80 | Overdue
295 | 13 | Train integration | Bella Mitchell | 2026-05-28 | 2026-05-26 | Done | 40
296 | 13 | Implement UAT plan | Kelly Anderson | 2025-11-24 | 2025-12-03 | Done | 8
297 | 13 | Document cutover | Sofia Young | 2026-01-31 | 2026-01-31 | Done | 80
298 | 13 | Plan cutover | Ravi Walker | 2025-11-30 |  | In Progress | 8 | Overdue
299 | 13 | Validate data model | Gavin Turner | 2026-04-19 |  | In Progress | 60 | Overdue
300 | 13 | Implement stakeholder briefing | Nina Morris | 2025-12-23 | 2025-12-20 | Done | 60
301 | 13 | Hand-off change request | Carlos Garcia | 2026-04-13 |  | In Progress | 80 | Overdue
302 | 13 | Plan test cases | Kyle Collins | 2025-11-17 |  | Open | 16 | Overdue
303 | 13 | Approve rollout plan | Nina Morris | 2026-04-25 |  | Open | 60 | Overdue
304 | 14 | Deploy stakeholder briefing | Theo Allen | 2026-06-04 | 2026-06-14 | Done | 24
305 | 14 | Deploy security review | Eli Nguyen | 2026-03-31 | 2026-04-05 | Done | 60
306 | 14 | Configure security review | Diana Roberts | 2026-02-12 |  | Open | 8 | Overdue
307 | 14 | Pilot vendor SOW | Uma King | 2026-04-25 | 2026-04-28 | Done | 60
308 | 14 | Implement test cases | Xavier Green | 2026-09-05 | 2026-09-10 | Done | 40
309 | 14 | Test security review | Hassan Davis | 2026-06-20 |  | Open | 16
310 | 14 | Review requirements | Sofia Young | 2026-05-23 |  | In Progress | 24
311 | 14 | Pilot training materials | Kyle Collins | 2026-07-04 | 2026-07-02 | Done | 60
312 | 14 | Implement security review | Gavin Turner | 2026-04-18 |  | Open | 24 | Overdue
313 | 14 | Draft data model | Zane Adams | 2026-06-04 | 2026-06-12 | Done | 40
314 | 14 | Test change request | Wendy Scott | 2026-05-25 |  | Blocked | 4
315 | 14 | Deploy cutover | Alex Johnson | 2026-02-09 | 2026-02-17 | Done | 80
316 | 14 | Kickoff training materials | Will Howard | 2026-02-24 | 2026-02-25 | Done | 24
317 | 14 | Draft change request | Jade Edwards | 2026-05-01 |  | Open | 8 | Overdue
318 | 14 | Configure cutover | Caleb Carter | 2026-04-30 | 2026-04-25 | Done | 80
319 | 15 | Review integration | Grace Khan | 2026-04-05 |  | In Progress | 24 | Overdue
320 | 15 | Validate training materials | Will Howard | 2026-01-31 | 2026-02-03 | Done | 8
321 | 15 | Configure cutover | Carlos Garcia | 2025-12-17 |  | In Progress | 4 | Overdue
322 | 15 | Document test cases | Ethan Phillips | 2025-11-06 |  | Open | 40 | Overdue
323 | 15 | Hand-off cutover | Imani Martin | 2026-02-21 |  | Open | 16 | Overdue
324 | 15 | Configure change request | Vera Cox | 2026-04-02 |  | Open | 80 | Overdue
325 | 15 | Validate RACI | Gavin Turner | 2026-01-12 |  | In Progress | 40 | Overdue
326 | 15 | Deploy security review | Brystal Patel | 2026-03-02 |  | In Progress | 16 | Overdue
327 | 15 | Configure change request | Theo Allen | 2026-01-20 |  | In Progress | 80 | Overdue
328 | 15 | Migrate UAT plan | Paige Cook | 2026-04-07 |  | Open | 80 | Overdue
329 | 15 | Kickoff requirements | Lena Reyes | 2026-03-25 |  | In Progress | 24 | Overdue
330 | 15 | Kickoff change request | Zoe Smith | 2025-12-10 |  | In Progress | 80 | Overdue
331 | 15 | Plan reports | Carlos Garcia | 2026-02-02 |  | Open | 40 | Overdue
332 | 15 | Migrate training materials | Aiden Hill | 2025-11-25 |  | Open | 8 | Overdue
333 | 15 | Configure cutover | Zoe Smith | 2026-02-10 |  | In Progress | 40 | Overdue
334 | 15 | Kickoff integration | Hailey Diaz | 2026-02-25 | 2026-02-19 | Done | 8
335 | 15 | Plan security review | Hailey Diaz | 2026-03-20 |  | Open | 24 | Overdue
336 | 15 | Migrate risk register | Ian Parker | 2026-01-16 |  | Blocked | 16 | Overdue
337 | 15 | Train RACI | Umar Bailey | 2026-03-16 |  | Open | 60 | Overdue
338 | 15 | Approve security review | Maya Jackson | 2026-04-10 | 2026-04-11 | Done | 8
339 | 15 | Test UAT plan | Zoe Smith | 2026-01-07 |  | In Progress | 16 | Overdue
340 | 15 | Migrate training materials | Ethan Phillips | 2025-12-20 |  | In Progress | 16 | Overdue
341 | 15 | Train vendor SOW | Ravi Walker | 2026-03-20 |  | Blocked | 16 | Overdue
342 | 16 | Configure risk register | Zane Adams | 2026-01-13 |  | In Progress | 80 | Overdue
343 | 16 | Train integration | Sofia Young | 2025-11-16 |  | Blocked | 4 | Overdue
344 | 16 | Review training materials | Caleb Carter | 2025-11-01 |  | Blocked | 60 | Overdue
345 | 16 | Test reports | Ian Parker | 2025-10-24 |  | In Progress | 16 | Overdue
346 | 16 | Implement data model | Nina Morris | 2026-01-10 |  | In Progress | 60 | Overdue
347 | 16 | Plan risk register | Hailey Diaz | 2025-10-20 |  | Open | 8 | Overdue
348 | 16 | Configure training materials | Tara Cooper | 2025-10-18 |  | Open | 24 | Overdue
349 | 16 | Implement requirements | Jade Edwards | 2025-09-14 |  | In Progress | 8 | Overdue
350 | 16 | Hand-off risk register | Ethan Phillips | 2025-12-02 |  | In Progress | 24 | Overdue
351 | 16 | Document UAT plan | Paige Cook | 2025-10-10 | 2025-10-12 | Done | 4
352 | 16 | Test cutover | Vera Cox | 2025-09-11 |  | In Progress | 60 | Overdue
353 | 16 | Configure risk register | Liam Thomas | 2025-08-29 | 2025-08-27 | Done | 4
354 | 16 | Hand-off vendor SOW | Sofia Young | 2025-11-29 | 2025-11-27 | Done | 4
355 | 16 | Approve data model | Victor Wright | 2025-08-22 |  | Open | 16 | Overdue
356 | 16 | Validate cutover | Fiona Evans | 2025-12-14 |  | Blocked | 8 | Overdue
357 | 16 | Test test cases | Hassan Davis | 2025-12-27 |  | In Progress | 16 | Overdue
358 | 16 | Plan UAT plan | Tara Cooper | 2025-09-30 |  | In Progress | 8 | Overdue
359 | 16 | Train UAT plan | Kyle Collins | 2025-08-23 |  | In Progress | 60 | Overdue
360 | 17 | Pilot rollout plan | Gavin Turner | 2026-02-23 | 2026-02-28 | Done | 16
361 | 17 | Implement integration | Ethan Phillips | 2026-02-12 | 2026-02-08 | Done | 16
362 | 17 | Configure reports | Caleb Carter | 2026-03-04 |  | Open | 80 | Overdue
363 | 17 | Deploy change request | Umar Bailey | 2026-03-07 |  | Blocked | 40 | Overdue
364 | 17 | Kickoff reports | Dana Lee | 2026-02-02 | 2026-02-06 | Done | 60
365 | 17 | Configure stakeholder briefing | Gavin Turner | 2026-02-16 | 2026-02-14 | Done | 60
366 | 17 | Plan risk register | Sofia Young | 2026-05-10 | 2026-05-06 | Done | 16
367 | 17 | Implement security review | Jorge Wilson | 2026-04-20 |  | In Progress | 24 | Overdue
368 | 17 | Document rollout plan | Sam Bell | 2026-05-07 |  | Blocked | 40
369 | 17 | Train reports | Rachel Morgan | 2026-04-02 | 2026-04-01 | Done | 80
370 | 17 | Validate security review | Hailey Diaz | 2026-04-18 | 2026-04-13 | Done | 60
371 | 17 | Approve data model | Dana Lee | 2026-03-19 |  | Open | 80 | Overdue
372 | 17 | Approve cutover | Jorge Wilson | 2026-04-12 | 2026-04-11 | Done | 8
373 | 17 | Review stakeholder briefing | Noah White | 2026-03-14 | 2026-03-21 | Done | 60
374 | 17 | Migrate test cases | Dana Lee | 2026-04-16 | 2026-04-25 | Done | 24
375 | 17 | Approve requirements | Jade Edwards | 2026-02-17 | 2026-02-24 | Done | 24
376 | 17 | Configure UAT plan | Alex Johnson | 2026-04-28 | 2026-04-21 | Done | 60
377 | 17 | Configure training materials | Sam Bell | 2026-02-28 | 2026-02-22 | Done | 4
378 | 17 | Hand-off risk register | Eli Nguyen | 2026-04-11 |  | Blocked | 24 | Overdue
379 | 17 | Train integration | Zoe Smith | 2026-02-05 | 2026-02-03 | Done | 60
380 | 17 | Document risk register | Yara Baker | 2026-05-05 | 2026-05-11 | Done | 24
381 | 18 | Plan RACI | Ian Parker | 2026-02-25 |  | Open | 8 | Overdue
382 | 18 | Implement cutover | Zane Adams | 2026-05-07 | 2026-05-03 | Done | 40
383 | 18 | Test RACI | Alex Johnson | 2025-12-23 |  | In Progress | 80 | Overdue
384 | 18 | Migrate stakeholder briefing | Umar Bailey | 2025-11-26 |  | Blocked | 40 | Overdue
385 | 18 | Pilot reports | Priya Clark | 2026-03-09 |  | In Progress | 24 | Overdue
386 | 18 | Test risk register | Umar Bailey | 2026-02-17 |  | Open | 80 | Overdue
387 | 18 | Plan rollout plan | Nina Morris | 2025-12-19 |  | Open | 80 | Overdue
388 | 18 | Test reports | Eli Nguyen | 2026-07-18 | 2026-07-11 | Done | 4
389 | 18 | Approve stakeholder briefing | Tara Cooper | 2026-04-22 |  | Open | 80 | Overdue
390 | 18 | Draft rollout plan | Caleb Carter | 2025-12-03 |  | Open | 8 | Overdue
391 | 18 | Pilot test cases | Dana Lee | 2026-04-08 |  | Open | 8 | Overdue
392 | 18 | Test RACI | Umar Bailey | 2026-03-29 |  | Blocked | 40 | Overdue
393 | 18 | Train stakeholder briefing | Uma King | 2026-02-10 |  | In Progress | 8 | Overdue
394 | 18 | Test rollout plan | Theo Allen | 2026-02-06 | 2026-02-15 | Done | 16
395 | 18 | Approve risk register | Vera Cox | 2025-12-06 |  | In Progress | 8 | Overdue
396 | 18 | Validate security review | Dana Lee | 2026-04-30 |  | In Progress | 16 | Overdue
397 | 18 | Configure test cases | Hailey Diaz | 2026-07-20 |  | In Progress | 16
398 | 18 | Implement UAT plan | Yara Baker | 2026-05-18 |  | In Progress | 8
399 | 18 | Test RACI | Olivia Harris | 2026-06-02 |  | In Progress | 16
400 | 18 | Train security review | Dana Lee | 2026-06-28 |  | In Progress | 40
401 | 18 | Validate cutover | Imani Martin | 2026-03-06 |  | Blocked | 24 | Overdue
402 | 18 | Document stakeholder briefing | Fatima Brown | 2026-01-22 |  | Open | 24 | Overdue
403 | 18 | Validate vendor SOW | Maya Jackson | 2026-06-25 |  | Open | 4
404 | 18 | Approve change request | Carlos Garcia | 2026-01-28 |  | Open | 80 | Overdue
405 | 18 | Train change request | Umar Bailey | 2025-12-09 |  | Open | 60 | Overdue
406 | 18 | Test RACI | Victor Wright | 2026-04-13 |  | Open | 16 | Overdue
407 | 18 | Hand-off reports | Vera Cox | 2026-07-11 |  | Open | 4
408 | 19 | Configure risk register | Priya Clark | 2026-06-07 | 2026-06-06 | Done | 40
409 | 19 | Migrate cutover | Paige Cook | 2026-07-17 | 2026-07-22 | Done | 16
410 | 19 | Validate risk register | Fiona Evans | 2026-07-10 |  | In Progress | 24
411 | 19 | Train RACI | Uma King | 2026-03-25 | 2026-04-02 | Done | 8
412 | 19 | Draft change request | Olivia Harris | 2026-08-11 |  | In Progress | 60
413 | 19 | Validate risk register | Lena Reyes | 2026-04-18 |  | Open | 40 | Overdue
414 | 19 | Test training materials | Olivia Harris | 2026-09-04 |  | In Progress | 24
415 | 19 | Validate stakeholder briefing | Rachel Morgan | 2026-11-21 | 2026-11-29 | Done | 16
416 | 19 | Kickoff stakeholder briefing | Vera Cox | 2026-06-14 | 2026-06-22 | Done | 24
417 | 19 | Train training materials | Kelly Anderson | 2026-09-26 |  | Open | 8
418 | 19 | Hand-off risk register | Ian Parker | 2026-11-09 |  | In Progress | 60
419 | 19 | Pilot stakeholder briefing | Dana Lee | 2026-03-05 | 2026-02-28 | Done | 80
420 | 19 | Pilot stakeholder briefing | Olivia Harris | 2026-02-06 |  | In Progress | 4 | Overdue
421 | 19 | Validate security review | Xavier Green | 2026-04-21 |  | Open | 4 | Overdue
422 | 19 | Plan security review | Brystal Patel | 2026-12-16 | 2026-12-24 | Done | 4
423 | 19 | Draft cutover | Umar Bailey | 2026-11-02 | 2026-10-26 | Done | 16
424 | 19 | Draft cutover | Sam Bell | 2026-11-04 |  | Blocked | 60
425 | 19 | Review risk register | Grace Khan | 2026-09-11 | 2026-09-09 | Done | 40
426 | 19 | Approve cutover | Quinn Lewis | 2026-04-20 |  | Open | 80 | Overdue
427 | 19 | Configure data model | Xavier Green | 2026-08-03 |  | In Progress | 24
428 | 19 | Deploy stakeholder briefing | Fatima Brown | 2026-09-26 | 2026-09-26 | Done | 60
429 | 19 | Configure rollout plan | Yara Baker | 2027-01-01 | 2026-12-27 | Done | 40
430 | 19 | Draft vendor SOW | Kelly Anderson | 2026-10-04 |  | Open | 4
431 | 19 | Approve RACI | Grace Khan | 2026-10-16 | 2026-10-19 | Done | 40
432 | 19 | Hand-off RACI | Sam Bell | 2026-02-24 |  | Open | 40 | Overdue
433 | 19 | Hand-off data model | Rachel Morgan | 2026-10-04 |  | In Progress | 16
434 | 19 | Implement risk register | Uma King | 2026-11-08 | 2026-11-02 | Done | 4
435 | 19 | Hand-off data model | Theo Allen | 2026-05-20 | 2026-05-25 | Done | 8
436 | 19 | Pilot RACI | Yara Baker | 2026-11-18 |  | Open | 60
437 | 19 | Train vendor SOW | Imani Martin | 2026-11-06 |  | In Progress | 80
438 | 20 | Document requirements | Grace Khan | 2026-04-11 |  | In Progress | 24 | Overdue
439 | 20 | Approve test cases | Nina Morris | 2025-11-24 | 2025-11-27 | Done | 40
440 | 20 | Document requirements | Owen Murphy | 2026-02-17 |  | Blocked | 16 | Overdue
441 | 20 | Document cutover | Yara Baker | 2026-03-16 |  | In Progress | 24 | Overdue
442 | 20 | Plan rollout plan | Fatima Brown | 2025-11-01 |  | In Progress | 80 | Overdue
443 | 20 | Test vendor SOW | Eli Nguyen | 2026-06-10 |  | Open | 4
444 | 20 | Kickoff test cases | Owen Murphy | 2025-12-13 |  | Open | 8 | Overdue
445 | 20 | Review data model | Alex Johnson | 2026-02-13 |  | Open | 16 | Overdue
446 | 20 | Deploy data model | Imani Martin | 2026-03-13 |  | Open | 4 | Overdue
447 | 20 | Validate cutover | Gavin Turner | 2025-11-01 |  | In Progress | 24 | Overdue
448 | 20 | Document cutover | Fatima Brown | 2025-09-19 |  | Open | 40 | Overdue
449 | 20 | Draft UAT plan | Aiden Hill | 2026-05-31 | 2026-06-05 | Done | 24
450 | 20 | Validate risk register | Priya Clark | 2025-09-10 |  | In Progress | 40 | Overdue
451 | 20 | Configure integration | Imani Martin | 2026-04-21 |  | Open | 16 | Overdue
452 | 20 | Implement data model | Kelly Anderson | 2025-12-30 |  | Open | 24 | Overdue
453 | 20 | Migrate test cases | Eli Nguyen | 2025-12-17 |  | In Progress | 16 | Overdue
454 | 20 | Approve change request | Maya Jackson | 2025-12-04 | 2025-12-12 | Done | 24
Formulas:
overdue_flag = IF(AND([status]<>"Done",[due_date]<TODAY()),"Overdue","")

## Data_TimeEntries_Wk
employee_id | employee | department | week_start | hours_this_week | capacity_flag
1 | Alex Johnson | Delivery | 2026-03-09 | 38.33 | OK
2 | Brystal Patel | Operations | 2026-03-09 | 63.74 | Overallocated
3 | Carlos Garcia | Finance | 2026-03-09 | 42.74 | OK
4 | Dana Lee | Operations | 2026-03-09 | 28.47 | Underutilized
5 | Eli Nguyen | Finance | 2026-03-09 | 35.98 | OK
6 | Fatima Brown | Operations | 2026-03-09 | 31.42 | OK
7 | Grace Khan | Operations | 2026-03-09 | 41.95 | OK
9 | Imani Martin | Delivery | 2026-03-09 | 35.76 | OK
11 | Kelly Anderson | Finance | 2026-03-09 | 41.29 | OK
12 | Liam Thomas | Finance | 2026-03-09 | 33.24 | OK
13 | Maya Jackson | PMO | 2026-03-09 | 37.67 | OK
14 | Noah White | Delivery | 2026-03-09 | 37.04 | OK
15 | Olivia Harris | Engineering | 2026-03-09 | 47.22 | Overallocated
16 | Priya Clark | Engineering | 2026-03-09 | 41.15 | OK
17 | Quinn Lewis | Finance | 2026-03-09 | 34.9 | OK
19 | Sofia Young | PMO | 2026-03-09 | 41.53 | OK
20 | Theo Allen | Delivery | 2026-03-09 | 41.54 | OK
21 | Uma King | Delivery | 2026-03-09 | 41.82 | OK
22 | Victor Wright | Operations | 2026-03-09 | 30.51 | OK
23 | Wendy Scott | Operations | 2026-03-09 | 38.03 | OK
24 | Xavier Green | PMO | 2026-03-09 | 33.51 | OK
25 | Yara Baker | Engineering | 2026-03-09 | 40.91 | OK
26 | Zane Adams | Delivery | 2026-03-09 | 39.74 | OK
28 | Bella Mitchell | Design | 2026-03-09 | 49.49 | Overallocated
29 | Caleb Carter | Finance | 2026-03-09 | 42.7 | OK
30 | Diana Roberts | PMO | 2026-03-09 | 36.81 | OK
32 | Fiona Evans | Delivery | 2026-03-09 | 37.35 | OK
34 | Hailey Diaz | Operations | 2026-03-09 | 47.67 | Overallocated
35 | Ian Parker | Finance | 2026-03-09 | 47.31 | Overallocated
36 | Jade Edwards | Engineering | 2026-03-09 | 51.94 | Overallocated
37 | Kyle Collins | Delivery | 2026-03-09 | 35 | OK
38 | Lena Reyes | Delivery | 2026-03-09 | 41.9 | OK
39 | Marcus Stewart | Operations | 2026-03-09 | 41.92 | OK
40 | Nina Morris | Engineering | 2026-03-09 | 45.02 | Overallocated
41 | Owen Murphy | Operations | 2026-03-09 | 48.91 | Overallocated
42 | Paige Cook | Design | 2026-03-09 | 52.84 | Overallocated
44 | Rachel Morgan | Delivery | 2026-03-09 | 42.09 | OK
45 | Sam Bell | Finance | 2026-03-09 | 37.09 | OK
46 | Tara Cooper | Operations | 2026-03-09 | 31.44 | OK
47 | Umar Bailey | Delivery | 2026-03-09 | 40.57 | OK
48 | Vera Cox | Operations | 2026-03-09 | 41.02 | OK
49 | Will Howard | Operations | 2026-03-09 | 43.88 | OK
1 | Alex Johnson | Delivery | 2026-03-16 | 40.82 | OK
2 | Brystal Patel | Operations | 2026-03-16 | 36.02 | OK
3 | Carlos Garcia | Finance | 2026-03-16 | 36.71 | OK
4 | Dana Lee | Operations | 2026-03-16 | 42.16 | OK
5 | Eli Nguyen | Finance | 2026-03-16 | 36.33 | OK
6 | Fatima Brown | Operations | 2026-03-16 | 36.83 | OK
8 | Hassan Davis | Operations | 2026-03-16 | 41.12 | OK
9 | Imani Martin | Delivery | 2026-03-16 | 49.84 | Overallocated
10 | Jorge Wilson | Finance | 2026-03-16 | 34.05 | OK
11 | Kelly Anderson | Finance | 2026-03-16 | 30.31 | OK
12 | Liam Thomas | Finance | 2026-03-16 | 40.72 | OK
13 | Maya Jackson | PMO | 2026-03-16 | 52.16 | Overallocated
14 | Noah White | Delivery | 2026-03-16 | 38.82 | OK
15 | Olivia Harris | Engineering | 2026-03-16 | 49.51 | Overallocated
16 | Priya Clark | Engineering | 2026-03-16 | 35.06 | OK
17 | Quinn Lewis | Finance | 2026-03-16 | 36.52 | OK
19 | Sofia Young | PMO | 2026-03-16 | 42.26 | OK
20 | Theo Allen | Delivery | 2026-03-16 | 39.29 | OK
21 | Uma King | Delivery | 2026-03-16 | 33.36 | OK
22 | Victor Wright | Operations | 2026-03-16 | 41.05 | OK
23 | Wendy Scott | Operations | 2026-03-16 | 28.16 | Underutilized
24 | Xavier Green | PMO | 2026-03-16 | 42.06 | OK
26 | Zane Adams | Delivery | 2026-03-16 | 42.57 | OK
27 | Aiden Hill | PMO | 2026-03-16 | 44.32 | OK
28 | Bella Mitchell | Design | 2026-03-16 | 33.54 | OK
29 | Caleb Carter | Finance | 2026-03-16 | 48.39 | Overallocated
31 | Ethan Phillips | Delivery | 2026-03-16 | 35.74 | OK
32 | Fiona Evans | Delivery | 2026-03-16 | 42.75 | OK
33 | Gavin Turner | Finance | 2026-03-16 | 38.43 | OK
34 | Hailey Diaz | Operations | 2026-03-16 | 44.22 | OK
35 | Ian Parker | Finance | 2026-03-16 | 45.99 | Overallocated
36 | Jade Edwards | Engineering | 2026-03-16 | 37.04 | OK
38 | Lena Reyes | Delivery | 2026-03-16 | 28.35 | Underutilized
39 | Marcus Stewart | Operations | 2026-03-16 | 35.82 | OK
40 | Nina Morris | Engineering | 2026-03-16 | 25.97 | Underutilized
41 | Owen Murphy | Operations | 2026-03-16 | 41.02 | OK
42 | Paige Cook | Design | 2026-03-16 | 46.92 | Overallocated
44 | Rachel Morgan | Delivery | 2026-03-16 | 39.04 | OK
45 | Sam Bell | Finance | 2026-03-16 | 38.92 | OK
46 | Tara Cooper | Operations | 2026-03-16 | 39.18 | OK
48 | Vera Cox | Operations | 2026-03-16 | 51.82 | Overallocated
49 | Will Howard | Operations | 2026-03-16 | 44.22 | OK
50 | Zoe Smith | Delivery | 2026-03-16 | 40.39 | OK
1 | Alex Johnson | Delivery | 2026-03-23 | 39.37 | OK
2 | Brystal Patel | Operations | 2026-03-23 | 43.13 | OK
3 | Carlos Garcia | Finance | 2026-03-23 | 51.16 | Overallocated
4 | Dana Lee | Operations | 2026-03-23 | 41.28 | OK
6 | Fatima Brown | Operations | 2026-03-23 | 41.53 | OK
7 | Grace Khan | Operations | 2026-03-23 | 27.03 | Underutilized
8 | Hassan Davis | Operations | 2026-03-23 | 46.59 | Overallocated
9 | Imani Martin | Delivery | 2026-03-23 | 48.83 | Overallocated
11 | Kelly Anderson | Finance | 2026-03-23 | 40.79 | OK
12 | Liam Thomas | Finance | 2026-03-23 | 32.67 | OK
13 | Maya Jackson | PMO | 2026-03-23 | 45.8 | Overallocated
14 | Noah White | Delivery | 2026-03-23 | 42.4 | OK
15 | Olivia Harris | Engineering | 2026-03-23 | 37.79 | OK
16 | Priya Clark | Engineering | 2026-03-23 | 40.38 | OK
19 | Sofia Young | PMO | 2026-03-23 | 51.19 | Overallocated
20 | Theo Allen | Delivery | 2026-03-23 | 29.19 | Underutilized
21 | Uma King | Delivery | 2026-03-23 | 39.52 | OK
22 | Victor Wright | Operations | 2026-03-23 | 35.22 | OK
23 | Wendy Scott | Operations | 2026-03-23 | 39.36 | OK
24 | Xavier Green | PMO | 2026-03-23 | 48.35 | Overallocated
26 | Zane Adams | Delivery | 2026-03-23 | 40.05 | OK
27 | Aiden Hill | PMO | 2026-03-23 | 41.11 | OK
28 | Bella Mitchell | Design | 2026-03-23 | 52.52 | Overallocated
29 | Caleb Carter | Finance | 2026-03-23 | 40.12 | OK
30 | Diana Roberts | PMO | 2026-03-23 | 48.5 | Overallocated
32 | Fiona Evans | Delivery | 2026-03-23 | 29.89 | Underutilized
34 | Hailey Diaz | Operations | 2026-03-23 | 48.22 | Overallocated
35 | Ian Parker | Finance | 2026-03-23 | 40.57 | OK
36 | Jade Edwards | Engineering | 2026-03-23 | 30.25 | OK
37 | Kyle Collins | Delivery | 2026-03-23 | 37.73 | OK
38 | Lena Reyes | Delivery | 2026-03-23 | 33.5 | OK
39 | Marcus Stewart | Operations | 2026-03-23 | 42.28 | OK
40 | Nina Morris | Engineering | 2026-03-23 | 28.98 | Underutilized
41 | Owen Murphy | Operations | 2026-03-23 | 25.38 | Underutilized
43 | Quincy Rogers | Finance | 2026-03-23 | 40.56 | OK
44 | Rachel Morgan | Delivery | 2026-03-23 | 35.49 | OK
45 | Sam Bell | Finance | 2026-03-23 | 33.28 | OK
46 | Tara Cooper | Operations | 2026-03-23 | 40.52 | OK
47 | Umar Bailey | Delivery | 2026-03-23 | 37.49 | OK
50 | Zoe Smith | Delivery | 2026-03-23 | 35.73 | OK
1 | Alex Johnson | Delivery | 2026-03-30 | 40.28 | OK
2 | Brystal Patel | Operations | 2026-03-30 | 41.8 | OK
3 | Carlos Garcia | Finance | 2026-03-30 | 58.53 | Overallocated
4 | Dana Lee | Operations | 2026-03-30 | 39.48 | OK
5 | Eli Nguyen | Finance | 2026-03-30 | 42.08 | OK
6 | Fatima Brown | Operations | 2026-03-30 | 40.47 | OK
7 | Grace Khan | Operations | 2026-03-30 | 25.81 | Underutilized
8 | Hassan Davis | Operations | 2026-03-30 | 50.76 | Overallocated
9 | Imani Martin | Delivery | 2026-03-30 | 48.42 | Overallocated
10 | Jorge Wilson | Finance | 2026-03-30 | 40.98 | OK
11 | Kelly Anderson | Finance | 2026-03-30 | 38.27 | OK
12 | Liam Thomas | Finance | 2026-03-30 | 42.25 | OK
13 | Maya Jackson | PMO | 2026-03-30 | 35 | OK
14 | Noah White | Delivery | 2026-03-30 | 35.27 | OK
15 | Olivia Harris | Engineering | 2026-03-30 | 37.11 | OK
17 | Quinn Lewis | Finance | 2026-03-30 | 30.43 | OK
18 | Ravi Walker | Operations | 2026-03-30 | 38.55 | OK
19 | Sofia Young | PMO | 2026-03-30 | 50.86 | Overallocated
20 | Theo Allen | Delivery | 2026-03-30 | 39.75 | OK
21 | Uma King | Delivery | 2026-03-30 | 40.01 | OK
22 | Victor Wright | Operations | 2026-03-30 | 32.42 | OK
23 | Wendy Scott | Operations | 2026-03-30 | 24.36 | Underutilized
24 | Xavier Green | PMO | 2026-03-30 | 32.81 | OK
25 | Yara Baker | Engineering | 2026-03-30 | 28.9 | Underutilized
26 | Zane Adams | Delivery | 2026-03-30 | 38.22 | OK
27 | Aiden Hill | PMO | 2026-03-30 | 43.2 | OK
29 | Caleb Carter | Finance | 2026-03-30 | 40.68 | OK
30 | Diana Roberts | PMO | 2026-03-30 | 42.22 | OK
31 | Ethan Phillips | Delivery | 2026-03-30 | 38.19 | OK
32 | Fiona Evans | Delivery | 2026-03-30 | 35.88 | OK
33 | Gavin Turner | Finance | 2026-03-30 | 36.71 | OK
34 | Hailey Diaz | Operations | 2026-03-30 | 36.82 | OK
35 | Ian Parker | Finance | 2026-03-30 | 40.9 | OK
36 | Jade Edwards | Engineering | 2026-03-30 | 36.59 | OK
37 | Kyle Collins | Delivery | 2026-03-30 | 50.17 | Overallocated
38 | Lena Reyes | Delivery | 2026-03-30 | 42.35 | OK
39 | Marcus Stewart | Operations | 2026-03-30 | 39.45 | OK
40 | Nina Morris | Engineering | 2026-03-30 | 47.83 | Overallocated
42 | Paige Cook | Design | 2026-03-30 | 40.79 | OK
43 | Quincy Rogers | Finance | 2026-03-30 | 43.36 | OK
44 | Rachel Morgan | Delivery | 2026-03-30 | 24.45 | Underutilized
45 | Sam Bell | Finance | 2026-03-30 | 47.9 | Overallocated
46 | Tara Cooper | Operations | 2026-03-30 | 34.53 | OK
47 | Umar Bailey | Delivery | 2026-03-30 | 51.71 | Overallocated
48 | Vera Cox | Operations | 2026-03-30 | 37.26 | OK
49 | Will Howard | Operations | 2026-03-30 | 36.09 | OK
50 | Zoe Smith | Delivery | 2026-03-30 | 36.99 | OK
2 | Brystal Patel | Operations | 2026-04-06 | 36.37 | OK
3 | Carlos Garcia | Finance | 2026-04-06 | 40.92 | OK
4 | Dana Lee | Operations | 2026-04-06 | 34.84 | OK
5 | Eli Nguyen | Finance | 2026-04-06 | 39.92 | OK
6 | Fatima Brown | Operations | 2026-04-06 | 49.4 | Overallocated
7 | Grace Khan | Operations | 2026-04-06 | 46.63 | Overallocated
10 | Jorge Wilson | Finance | 2026-04-06 | 41.84 | OK
11 | Kelly Anderson | Finance | 2026-04-06 | 39.38 | OK
12 | Liam Thomas | Finance | 2026-04-06 | 35.99 | OK
13 | Maya Jackson | PMO | 2026-04-06 | 42.64 | OK
15 | Olivia Harris | Engineering | 2026-04-06 | 27.78 | Underutilized
16 | Priya Clark | Engineering | 2026-04-06 | 35.61 | OK
17 | Quinn Lewis | Finance | 2026-04-06 | 39.94 | OK
18 | Ravi Walker | Operations | 2026-04-06 | 48.91 | Overallocated
21 | Uma King | Delivery | 2026-04-06 | 49.91 | Overallocated
22 | Victor Wright | Operations | 2026-04-06 | 50.91 | Overallocated
23 | Wendy Scott | Operations | 2026-04-06 | 32.13 | OK
24 | Xavier Green | PMO | 2026-04-06 | 42.83 | OK
25 | Yara Baker | Engineering | 2026-04-06 | 41.33 | OK
26 | Zane Adams | Delivery | 2026-04-06 | 45.28 | Overallocated
27 | Aiden Hill | PMO | 2026-04-06 | 46.06 | Overallocated
29 | Caleb Carter | Finance | 2026-04-06 | 47.44 | Overallocated
30 | Diana Roberts | PMO | 2026-04-06 | 44.33 | OK
31 | Ethan Phillips | Delivery | 2026-04-06 | 45.85 | Overallocated
32 | Fiona Evans | Delivery | 2026-04-06 | 38.48 | OK
33 | Gavin Turner | Finance | 2026-04-06 | 37.94 | OK
34 | Hailey Diaz | Operations | 2026-04-06 | 54.73 | Overallocated
36 | Jade Edwards | Engineering | 2026-04-06 | 47.43 | Overallocated
37 | Kyle Collins | Delivery | 2026-04-06 | 40.02 | OK
38 | Lena Reyes | Delivery | 2026-04-06 | 36.87 | OK
40 | Nina Morris | Engineering | 2026-04-06 | 34.48 | OK
41 | Owen Murphy | Operations | 2026-04-06 | 57.56 | Overallocated
42 | Paige Cook | Design | 2026-04-06 | 38.76 | OK
43 | Quincy Rogers | Finance | 2026-04-06 | 34.62 | OK
44 | Rachel Morgan | Delivery | 2026-04-06 | 49.45 | Overallocated
45 | Sam Bell | Finance | 2026-04-06 | 46.57 | Overallocated
46 | Tara Cooper | Operations | 2026-04-06 | 36.4 | OK
47 | Umar Bailey | Delivery | 2026-04-06 | 35.24 | OK
48 | Vera Cox | Operations | 2026-04-06 | 29.29 | Underutilized
49 | Will Howard | Operations | 2026-04-06 | 37.16 | OK
50 | Zoe Smith | Delivery | 2026-04-06 | 40.36 | OK
2 | Brystal Patel | Operations | 2026-04-13 | 39.09 | OK
3 | Carlos Garcia | Finance | 2026-04-13 | 42.57 | OK
4 | Dana Lee | Operations | 2026-04-13 | 42.72 | OK
5 | Eli Nguyen | Finance | 2026-04-13 | 39.58 | OK
7 | Grace Khan | Operations | 2026-04-13 | 45.9 | Overallocated
8 | Hassan Davis | Operations | 2026-04-13 | 28.79 | Underutilized
9 | Imani Martin | Delivery | 2026-04-13 | 37.69 | OK
10 | Jorge Wilson | Finance | 2026-04-13 | 47.1 | Overallocated
11 | Kelly Anderson | Finance | 2026-04-13 | 36.43 | OK
12 | Liam Thomas | Finance | 2026-04-13 | 38.93 | OK
13 | Maya Jackson | PMO | 2026-04-13 | 29.09 | Underutilized
14 | Noah White | Delivery | 2026-04-13 | 28.67 | Underutilized
15 | Olivia Harris | Engineering | 2026-04-13 | 35.91 | OK
17 | Quinn Lewis | Finance | 2026-04-13 | 43.54 | OK
18 | Ravi Walker | Operations | 2026-04-13 | 41.44 | OK
19 | Sofia Young | PMO | 2026-04-13 | 48.91 | Overallocated
20 | Theo Allen | Delivery | 2026-04-13 | 42.66 | OK
21 | Uma King | Delivery | 2026-04-13 | 39.14 | OK
22 | Victor Wright | Operations | 2026-04-13 | 51.85 | Overallocated
23 | Wendy Scott | Operations | 2026-04-13 | 50.83 | Overallocated
24 | Xavier Green | PMO | 2026-04-13 | 46.91 | Overallocated
25 | Yara Baker | Engineering | 2026-04-13 | 32.09 | OK
26 | Zane Adams | Delivery | 2026-04-13 | 43.07 | OK
27 | Aiden Hill | PMO | 2026-04-13 | 54.42 | Overallocated
28 | Bella Mitchell | Design | 2026-04-13 | 34.67 | OK
29 | Caleb Carter | Finance | 2026-04-13 | 34.91 | OK
30 | Diana Roberts | PMO | 2026-04-13 | 39.97 | OK
31 | Ethan Phillips | Delivery | 2026-04-13 | 35.96 | OK
32 | Fiona Evans | Delivery | 2026-04-13 | 35.24 | OK
33 | Gavin Turner | Finance | 2026-04-13 | 47.1 | Overallocated
34 | Hailey Diaz | Operations | 2026-04-13 | 32.02 | OK
35 | Ian Parker | Finance | 2026-04-13 | 37.57 | OK
36 | Jade Edwards | Engineering | 2026-04-13 | 29.97 | Underutilized
37 | Kyle Collins | Delivery | 2026-04-13 | 41.04 | OK
38 | Lena Reyes | Delivery | 2026-04-13 | 33.69 | OK
39 | Marcus Stewart | Operations | 2026-04-13 | 48.9 | Overallocated
40 | Nina Morris | Engineering | 2026-04-13 | 46.96 | Overallocated
41 | Owen Murphy | Operations | 2026-04-13 | 48.71 | Overallocated
42 | Paige Cook | Design | 2026-04-13 | 49.22 | Overallocated
43 | Quincy Rogers | Finance | 2026-04-13 | 50.67 | Overallocated
44 | Rachel Morgan | Delivery | 2026-04-13 | 42.7 | OK
45 | Sam Bell | Finance | 2026-04-13 | 41.29 | OK
46 | Tara Cooper | Operations | 2026-04-13 | 39.8 | OK
47 | Umar Bailey | Delivery | 2026-04-13 | 43.65 | OK
48 | Vera Cox | Operations | 2026-04-13 | 41.73 | OK
49 | Will Howard | Operations | 2026-04-13 | 37.69 | OK
50 | Zoe Smith | Delivery | 2026-04-13 | 39.33 | OK
1 | Alex Johnson | Delivery | 2026-04-20 | 32.48 | OK
2 | Brystal Patel | Operations | 2026-04-20 | 33.26 | OK
3 | Carlos Garcia | Finance | 2026-04-20 | 38.61 | OK
4 | Dana Lee | Operations | 2026-04-20 | 49.02 | Overallocated
5 | Eli Nguyen | Finance | 2026-04-20 | 25.83 | Underutilized
6 | Fatima Brown | Operations | 2026-04-20 | 31.68 | OK
7 | Grace Khan | Operations | 2026-04-20 | 39.48 | OK
8 | Hassan Davis | Operations | 2026-04-20 | 34.07 | OK
9 | Imani Martin | Delivery | 2026-04-20 | 34.89 | OK
10 | Jorge Wilson | Finance | 2026-04-20 | 38.76 | OK
11 | Kelly Anderson | Finance | 2026-04-20 | 27.72 | Underutilized
12 | Liam Thomas | Finance | 2026-04-20 | 44.43 | OK
13 | Maya Jackson | PMO | 2026-04-20 | 52.26 | Overallocated
14 | Noah White | Delivery | 2026-04-20 | 48.91 | Overallocated
15 | Olivia Harris | Engineering | 2026-04-20 | 34.18 | OK
17 | Quinn Lewis | Finance | 2026-04-20 | 39.23 | OK
18 | Ravi Walker | Operations | 2026-04-20 | 39.38 | OK
19 | Sofia Young | PMO | 2026-04-20 | 39.75 | OK
20 | Theo Allen | Delivery | 2026-04-20 | 35.66 | OK
22 | Victor Wright | Operations | 2026-04-20 | 39.67 | OK
23 | Wendy Scott | Operations | 2026-04-20 | 32.83 | OK
24 | Xavier Green | PMO | 2026-04-20 | 41.94 | OK
25 | Yara Baker | Engineering | 2026-04-20 | 39.46 | OK
26 | Zane Adams | Delivery | 2026-04-20 | 39.2 | OK
27 | Aiden Hill | PMO | 2026-04-20 | 36 | OK
28 | Bella Mitchell | Design | 2026-04-20 | 37.89 | OK
29 | Caleb Carter | Finance | 2026-04-20 | 46.87 | Overallocated
30 | Diana Roberts | PMO | 2026-04-20 | 28.32 | Underutilized
31 | Ethan Phillips | Delivery | 2026-04-20 | 52.45 | Overallocated
33 | Gavin Turner | Finance | 2026-04-20 | 48.97 | Overallocated
34 | Hailey Diaz | Operations | 2026-04-20 | 40.2 | OK
35 | Ian Parker | Finance | 2026-04-20 | 34.63 | OK
36 | Jade Edwards | Engineering | 2026-04-20 | 36.67 | OK
37 | Kyle Collins | Delivery | 2026-04-20 | 42.39 | OK
38 | Lena Reyes | Delivery | 2026-04-20 | 51.92 | Overallocated
39 | Marcus Stewart | Operations | 2026-04-20 | 49.9 | Overallocated
40 | Nina Morris | Engineering | 2026-04-20 | 43.2 | OK
41 | Owen Murphy | Operations | 2026-04-20 | 41.3 | OK
42 | Paige Cook | Design | 2026-04-20 | 39.64 | OK
43 | Quincy Rogers | Finance | 2026-04-20 | 47.4 | Overallocated
44 | Rachel Morgan | Delivery | 2026-04-20 | 38.37 | OK
45 | Sam Bell | Finance | 2026-04-20 | 32.28 | OK
46 | Tara Cooper | Operations | 2026-04-20 | 26.8 | Underutilized
47 | Umar Bailey | Delivery | 2026-04-20 | 38.5 | OK
50 | Zoe Smith | Delivery | 2026-04-20 | 37.34 | OK
2 | Brystal Patel | Operations | 2026-04-27 | 47.99 | Overallocated
3 | Carlos Garcia | Finance | 2026-04-27 | 41.83 | OK
4 | Dana Lee | Operations | 2026-04-27 | 44.67 | OK
5 | Eli Nguyen | Finance | 2026-04-27 | 41.14 | OK
6 | Fatima Brown | Operations | 2026-04-27 | 37.21 | OK
7 | Grace Khan | Operations | 2026-04-27 | 39.03 | OK
8 | Hassan Davis | Operations | 2026-04-27 | 37.96 | OK
9 | Imani Martin | Delivery | 2026-04-27 | 37.1 | OK
10 | Jorge Wilson | Finance | 2026-04-27 | 34.88 | OK
11 | Kelly Anderson | Finance | 2026-04-27 | 45.5 | Overallocated
13 | Maya Jackson | PMO | 2026-04-27 | 38.91 | OK
16 | Priya Clark | Engineering | 2026-04-27 | 34.39 | OK
17 | Quinn Lewis | Finance | 2026-04-27 | 50.12 | Overallocated
18 | Ravi Walker | Operations | 2026-04-27 | 34.26 | OK
19 | Sofia Young | PMO | 2026-04-27 | 38.19 | OK
20 | Theo Allen | Delivery | 2026-04-27 | 48.45 | Overallocated
21 | Uma King | Delivery | 2026-04-27 | 47.13 | Overallocated
22 | Victor Wright | Operations | 2026-04-27 | 51.2 | Overallocated
23 | Wendy Scott | Operations | 2026-04-27 | 42.32 | OK
24 | Xavier Green | PMO | 2026-04-27 | 41.83 | OK
25 | Yara Baker | Engineering | 2026-04-27 | 47.84 | Overallocated
26 | Zane Adams | Delivery | 2026-04-27 | 65.28 | Overallocated
27 | Aiden Hill | PMO | 2026-04-27 | 46.75 | Overallocated
30 | Diana Roberts | PMO | 2026-04-27 | 28.11 | Underutilized
31 | Ethan Phillips | Delivery | 2026-04-27 | 41.05 | OK
32 | Fiona Evans | Delivery | 2026-04-27 | 43.02 | OK
33 | Gavin Turner | Finance | 2026-04-27 | 42.09 | OK
34 | Hailey Diaz | Operations | 2026-04-27 | 46.51 | Overallocated
35 | Ian Parker | Finance | 2026-04-27 | 38.5 | OK
36 | Jade Edwards | Engineering | 2026-04-27 | 52.57 | Overallocated
37 | Kyle Collins | Delivery | 2026-04-27 | 39.6 | OK
38 | Lena Reyes | Delivery | 2026-04-27 | 34.92 | OK
39 | Marcus Stewart | Operations | 2026-04-27 | 35.41 | OK
40 | Nina Morris | Engineering | 2026-04-27 | 40.99 | OK
41 | Owen Murphy | Operations | 2026-04-27 | 40.95 | OK
43 | Quincy Rogers | Finance | 2026-04-27 | 26.84 | Underutilized
44 | Rachel Morgan | Delivery | 2026-04-27 | 40.57 | OK
45 | Sam Bell | Finance | 2026-04-27 | 51.27 | Overallocated
46 | Tara Cooper | Operations | 2026-04-27 | 33.54 | OK
47 | Umar Bailey | Delivery | 2026-04-27 | 49.66 | Overallocated
49 | Will Howard | Operations | 2026-04-27 | 27.02 | Underutilized
50 | Zoe Smith | Delivery | 2026-04-27 | 27.81 | Underutilized

## Data_Budget
record_id | project_id | project_name | month_start | budgeted_amount | actual_amount | variance
1 | 1 | ERP Implementation | 2025-06-01 | 4946.34 | 8607.51 | 3661.17
2 | 1 | ERP Implementation | 2025-07-01 | 4808.32 | 7081.54 | 2273.22
3 | 1 | ERP Implementation | 2025-08-01 | 4850.62 | 4395.82 | -454.8
4 | 1 | ERP Implementation | 2025-09-01 | 5382.81 | 8182.51 | 2799.7
5 | 1 | ERP Implementation | 2025-10-01 | 4999.37 | 3941.84 | -1057.53
6 | 1 | ERP Implementation | 2025-11-01 | 5378.7 | 4630.66 | -748.04
7 | 1 | ERP Implementation | 2025-12-01 | 4824.8 | 4583.3 | -241.5
8 | 1 | ERP Implementation | 2026-01-01 | 4888.47 | 6192.54 | 1304.07
9 | 1 | ERP Implementation | 2026-02-01 | 4944.07 | 5426.9 | 482.83
10 | 1 | ERP Implementation | 2026-03-01 | 5322.23 | 6069.2 | 746.97
11 | 1 | ERP Implementation | 2026-04-01 | 4810.57 | 4183.61 | -626.96
12 | 1 | ERP Implementation | 2026-05-01 | 5263.67 | 7275.83 | 2012.16
13 | 2 | CRM Migration | 2025-06-01 | 6328.68 | 5173.61 | -1155.07
14 | 2 | CRM Migration | 2025-07-01 | 6634.93 | 4842.05 | -1792.88
15 | 2 | CRM Migration | 2025-08-01 | 6307.79 | 3736.28 | -2571.51
16 | 2 | CRM Migration | 2025-09-01 | 6631.61 | 6071.54 | -560.07
17 | 2 | CRM Migration | 2025-10-01 | 6257.09 | 5068.67 | -1188.42
18 | 2 | CRM Migration | 2025-11-01 | 7088.19 | 6942.06 | -146.13
19 | 2 | CRM Migration | 2025-12-01 | 6661.24 | 5331.65 | -1329.59
20 | 2 | CRM Migration | 2026-01-01 | 6604.29 | 6831 | 226.71
21 | 2 | CRM Migration | 2026-02-01 | 7188.07 | 5662.31 | -1525.76
22 | 2 | CRM Migration | 2026-03-01 | 6731.58 | 4859.25 | -1872.33
23 | 2 | CRM Migration | 2026-04-01 | 6621.61 | 3834.03 | -2787.58
24 | 2 | CRM Migration | 2026-05-01 | 6253.32 | 3285.4 | -2967.92
25 | 3 | Cloud Cost Optimization | 2025-06-01 | 26067.39 | 15996.68 | -10070.71
26 | 3 | Cloud Cost Optimization | 2025-07-01 | 23722.28 | 19586.82 | -4135.46
27 | 3 | Cloud Cost Optimization | 2025-08-01 | 26681.65 | 16988.48 | -9693.17
28 | 3 | Cloud Cost Optimization | 2025-09-01 | 23984.63 | 18420.31 | -5564.32
29 | 3 | Cloud Cost Optimization | 2025-10-01 | 24992.44 | 28232.15 | 3239.71
30 | 3 | Cloud Cost Optimization | 2025-11-01 | 23377.22 | 26717.78 | 3340.56
31 | 3 | Cloud Cost Optimization | 2025-12-01 | 24314.63 | 28011.6 | 3696.97
32 | 3 | Cloud Cost Optimization | 2026-01-01 | 24137.13 | 23392.36 | -744.77
33 | 3 | Cloud Cost Optimization | 2026-02-01 | 26925.34 | 25171.66 | -1753.68
34 | 3 | Cloud Cost Optimization | 2026-03-01 | 23487.96 | 17142.78 | -6345.18
35 | 3 | Cloud Cost Optimization | 2026-04-01 | 24494.23 | 31136.52 | 6642.29
36 | 3 | Cloud Cost Optimization | 2026-05-01 | 26716.59 | 13432.94 | -13283.65
37 | 4 | Cybersecurity Uplift | 2025-06-01 | 35719.56 | 34379.09 | -1340.47
38 | 4 | Cybersecurity Uplift | 2025-07-01 | 35999.05 | 24942.75 | -11056.3
39 | 4 | Cybersecurity Uplift | 2025-08-01 | 35503.35 | 38756.62 | 3253.27
40 | 4 | Cybersecurity Uplift | 2025-09-01 | 34917.51 | 46681.74 | 11764.23
41 | 4 | Cybersecurity Uplift | 2025-10-01 | 31356.37 | 39385 | 8028.63
42 | 4 | Cybersecurity Uplift | 2025-11-01 | 35270.82 | 44140.63 | 8869.81
43 | 4 | Cybersecurity Uplift | 2025-12-01 | 34941.64 | 32642.75 | -2298.89
44 | 4 | Cybersecurity Uplift | 2026-01-01 | 32175.75 | 45090.13 | 12914.38
45 | 4 | Cybersecurity Uplift | 2026-02-01 | 34923.45 | 34567.67 | -355.78
46 | 4 | Cybersecurity Uplift | 2026-03-01 | 34633.6 | 25422.23 | -9211.37
47 | 4 | Cybersecurity Uplift | 2026-04-01 | 33584.83 | 43948.74 | 10363.91
48 | 4 | Cybersecurity Uplift | 2026-05-01 | 33878.89 | 38528.25 | 4649.36
49 | 5 | Data Warehouse Rebuild | 2025-06-01 | 5240.88 | 1816.82 | -3424.06
50 | 5 | Data Warehouse Rebuild | 2025-07-01 | 5188.71 | 1789.56 | -3399.15
51 | 5 | Data Warehouse Rebuild | 2025-08-01 | 5337.36 | 2748.96 | -2588.4
52 | 5 | Data Warehouse Rebuild | 2025-09-01 | 5322.99 | 2076.65 | -3246.34
53 | 5 | Data Warehouse Rebuild | 2025-10-01 | 5082.81 | 1392.69 | -3690.12
54 | 5 | Data Warehouse Rebuild | 2025-11-01 | 4887.24 | 1731.97 | -3155.27
55 | 5 | Data Warehouse Rebuild | 2025-12-01 | 4676.89 | 2057.83 | -2619.06
56 | 5 | Data Warehouse Rebuild | 2026-01-01 | 4893.97 | 2082.94 | -2811.03
57 | 5 | Data Warehouse Rebuild | 2026-02-01 | 4759.9 | 2525.36 | -2234.54
58 | 5 | Data Warehouse Rebuild | 2026-03-01 | 4956.35 | 3080.74 | -1875.61
59 | 5 | Data Warehouse Rebuild | 2026-04-01 | 4910.47 | 1634.21 | -3276.26
60 | 5 | Data Warehouse Rebuild | 2026-05-01 | 4814.78 | 1895.23 | -2919.55
61 | 6 | Customer Portal Refresh | 2025-06-01 | 33478.82 | 16049.35 | -17429.47
62 | 6 | Customer Portal Refresh | 2025-07-01 | 34118.54 | 22396.99 | -11721.55
63 | 6 | Customer Portal Refresh | 2025-08-01 | 31114.51 | 21359.78 | -9754.73
64 | 6 | Customer Portal Refresh | 2025-09-01 | 33163.84 | 17885.63 | -15278.21
65 | 6 | Customer Portal Refresh | 2025-10-01 | 31088.98 | 26372.92 | -4716.06
66 | 6 | Customer Portal Refresh | 2025-11-01 | 34941.57 | 16101.41 | -18840.16
67 | 6 | Customer Portal Refresh | 2025-12-01 | 32268.76 | 24131.48 | -8137.28
68 | 6 | Customer Portal Refresh | 2026-01-01 | 35915.66 | 32916.76 | -2998.9
69 | 6 | Customer Portal Refresh | 2026-02-01 | 34316.34 | 27246.88 | -7069.46
70 | 6 | Customer Portal Refresh | 2026-03-01 | 32268.85 | 26696.2 | -5572.65
71 | 6 | Customer Portal Refresh | 2026-04-01 | 31992.82 | 27957.36 | -4035.46
72 | 6 | Customer Portal Refresh | 2026-05-01 | 32947.9 | 32102.96 | -844.94
73 | 7 | Mobile App Launch | 2025-06-01 | 25962.06 | 12118.67 | -13843.39
74 | 7 | Mobile App Launch | 2025-07-01 | 24851.52 | 15530.8 | -9320.72
75 | 7 | Mobile App Launch | 2025-08-01 | 26144.71 | 11768.62 | -14376.09
76 | 7 | Mobile App Launch | 2025-09-01 | 26371.64 | 11742.88 | -14628.76
77 | 7 | Mobile App Launch | 2025-10-01 | 23181.03 | 10833.44 | -12347.59
78 | 7 | Mobile App Launch | 2025-11-01 | 24665.01 | 11314.44 | -13350.57
79 | 7 | Mobile App Launch | 2025-12-01 | 25817.51 | 13695.83 | -12121.68
80 | 7 | Mobile App Launch | 2026-01-01 | 24255.79 | 14557.6 | -9698.19
81 | 7 | Mobile App Launch | 2026-02-01 | 25896.38 | 10297.26 | -15599.12
82 | 7 | Mobile App Launch | 2026-03-01 | 26029.42 | 12440.72 | -13588.7
83 | 7 | Mobile App Launch | 2026-04-01 | 24799.79 | 14146.09 | -10653.7
84 | 7 | Mobile App Launch | 2026-05-01 | 26231.34 | 7137.74 | -19093.6
85 | 8 | HR Systems Consolidation | 2025-06-01 | 24840.65 | 15628.08 | -9212.57
86 | 8 | HR Systems Consolidation | 2025-07-01 | 24620.37 | 14615.27 | -10005.1
87 | 8 | HR Systems Consolidation | 2025-08-01 | 25630.87 | 9003.99 | -16626.88
88 | 8 | HR Systems Consolidation | 2025-09-01 | 25976.99 | 7759.37 | -18217.62
89 | 8 | HR Systems Consolidation | 2025-10-01 | 25903.65 | 16228.38 | -9675.27
90 | 8 | HR Systems Consolidation | 2025-11-01 | 24211.2 | 9456.02 | -14755.18
91 | 8 | HR Systems Consolidation | 2025-12-01 | 26252.53 | 13335.53 | -12917
92 | 8 | HR Systems Consolidation | 2026-01-01 | 25466.98 | 11090.69 | -14376.29
93 | 8 | HR Systems Consolidation | 2026-02-01 | 25762.65 | 7194.39 | -18568.26
94 | 8 | HR Systems Consolidation | 2026-03-01 | 26852.57 | 10726.57 | -16126
95 | 8 | HR Systems Consolidation | 2026-04-01 | 25700.41 | 7151.19 | -18549.22
96 | 8 | HR Systems Consolidation | 2026-05-01 | 26218.56 | 13170.57 | -13047.99
97 | 9 | Compliance Remediation | 2025-06-01 | 9337.75 | 8382.61 | -955.14
98 | 9 | Compliance Remediation | 2025-07-01 | 10431.55 | 8910.01 | -1521.54
99 | 9 | Compliance Remediation | 2025-08-01 | 9437.07 | 14830.75 | 5393.68
100 | 9 | Compliance Remediation | 2025-09-01 | 9875.01 | 13694.88 | 3819.87
101 | 9 | Compliance Remediation | 2025-10-01 | 9386.33 | 8885.57 | -500.76
102 | 9 | Compliance Remediation | 2025-11-01 | 10643.86 | 7356.95 | -3286.91
103 | 9 | Compliance Remediation | 2025-12-01 | 10382.05 | 11659.49 | 1277.44
104 | 9 | Compliance Remediation | 2026-01-01 | 9912.43 | 8477.7 | -1434.73
105 | 9 | Compliance Remediation | 2026-02-01 | 9976.07 | 9392.81 | -583.26
106 | 9 | Compliance Remediation | 2026-03-01 | 9231.4 | 15078.14 | 5846.74
107 | 9 | Compliance Remediation | 2026-04-01 | 9919.23 | 15230.61 | 5311.38
108 | 9 | Compliance Remediation | 2026-05-01 | 9588.21 | 12203.72 | 2615.51
109 | 10 | Procurement Automation | 2025-06-01 | 4919.74 | 4293.11 | -626.63
110 | 10 | Procurement Automation | 2025-07-01 | 5010.68 | 3103.35 | -1907.33
111 | 10 | Procurement Automation | 2025-08-01 | 5179.69 | 2946.02 | -2233.67
112 | 10 | Procurement Automation | 2025-09-01 | 5348.22 | 2317.63 | -3030.59
113 | 10 | Procurement Automation | 2025-10-01 | 5324.06 | 4342.53 | -981.53
114 | 10 | Procurement Automation | 2025-11-01 | 5294.11 | 3212.22 | -2081.89
115 | 10 | Procurement Automation | 2025-12-01 | 4785.52 | 3168.46 | -1617.06
116 | 10 | Procurement Automation | 2026-01-01 | 4648.56 | 3385.95 | -1262.61
117 | 10 | Procurement Automation | 2026-02-01 | 4615.22 | 3611.44 | -1003.78
118 | 10 | Procurement Automation | 2026-03-01 | 5061.12 | 4025.73 | -1035.39
119 | 10 | Procurement Automation | 2026-04-01 | 5042.6 | 4754.04 | -288.56
120 | 10 | Procurement Automation | 2026-05-01 | 4814.28 | 2139.2 | -2675.08
121 | 11 | Reporting Modernization | 2025-06-01 | 10295.96 | 11380.7 | 1084.74
122 | 11 | Reporting Modernization | 2025-07-01 | 10674.78 | 6019.25 | -4655.53
123 | 11 | Reporting Modernization | 2025-08-01 | 10565.53 | 9530.76 | -1034.77
124 | 11 | Reporting Modernization | 2025-09-01 | 10344.32 | 9693.8 | -650.52
125 | 11 | Reporting Modernization | 2025-10-01 | 9949.55 | 8320.08 | -1629.47
126 | 11 | Reporting Modernization | 2025-11-01 | 10613.08 | 8236.1 | -2376.98
127 | 11 | Reporting Modernization | 2025-12-01 | 10356.79 | 6327.47 | -4029.32
128 | 11 | Reporting Modernization | 2026-01-01 | 9824.59 | 10249.45 | 424.86
129 | 11 | Reporting Modernization | 2026-02-01 | 9866.98 | 8465.3 | -1401.68
130 | 11 | Reporting Modernization | 2026-03-01 | 10705.92 | 8249.16 | -2456.76
131 | 11 | Reporting Modernization | 2026-04-01 | 10244 | 8731.88 | -1512.12
132 | 11 | Reporting Modernization | 2026-05-01 | 9776.41 | 9287.49 | -488.92
133 | 12 | Network Upgrade | 2025-06-01 | 6383.7 | 4424.26 | -1959.44
134 | 12 | Network Upgrade | 2025-07-01 | 6727.29 | 2344.67 | -4382.62
135 | 12 | Network Upgrade | 2025-08-01 | 7199.21 | 2460.83 | -4738.38
136 | 12 | Network Upgrade | 2025-09-01 | 6516.04 | 3703.8 | -2812.24
137 | 12 | Network Upgrade | 2025-10-01 | 6411.53 | 2149.71 | -4261.82
138 | 12 | Network Upgrade | 2025-11-01 | 6855.39 | 3169.56 | -3685.83
139 | 12 | Network Upgrade | 2025-12-01 | 6319.7 | 2373.63 | -3946.07
140 | 12 | Network Upgrade | 2026-01-01 | 7050.09 | 2329.98 | -4720.11
141 | 12 | Network Upgrade | 2026-02-01 | 6670.38 | 3193.45 | -3476.93
142 | 12 | Network Upgrade | 2026-03-01 | 6993.94 | 3968.04 | -3025.9
143 | 12 | Network Upgrade | 2026-04-01 | 6493.58 | 4352.56 | -2141.02
144 | 12 | Network Upgrade | 2026-05-01 | 6254.9 | 3197.41 | -3057.49
145 | 13 | Onboarding Redesign | 2025-06-01 | 4640.34 | 1979.94 | -2660.4
146 | 13 | Onboarding Redesign | 2025-07-01 | 5357.01 | 1865.82 | -3491.19
147 | 13 | Onboarding Redesign | 2025-08-01 | 5239.19 | 2631.39 | -2607.8
148 | 13 | Onboarding Redesign | 2025-09-01 | 5370.12 | 2316.33 | -3053.79
149 | 13 | Onboarding Redesign | 2025-10-01 | 5204.61 | 2292.92 | -2911.69
150 | 13 | Onboarding Redesign | 2025-11-01 | 5379.73 | 2294 | -3085.73
151 | 13 | Onboarding Redesign | 2025-12-01 | 5225.32 | 1972.45 | -3252.87
152 | 13 | Onboarding Redesign | 2026-01-01 | 5087.72 | 2484.49 | -2603.23
153 | 13 | Onboarding Redesign | 2026-02-01 | 5286.71 | 2419.73 | -2866.98
154 | 13 | Onboarding Redesign | 2026-03-01 | 4681.49 | 2450.35 | -2231.14
155 | 13 | Onboarding Redesign | 2026-04-01 | 5049.98 | 2043.78 | -3006.2
156 | 13 | Onboarding Redesign | 2026-05-01 | 5005.84 | 1289 | -3716.84
157 | 14 | Inventory Visibility | 2025-06-01 | 19839.63 | 9907.98 | -9931.65
158 | 14 | Inventory Visibility | 2025-07-01 | 22398.79 | 10904.72 | -11494.07
159 | 14 | Inventory Visibility | 2025-08-01 | 21730.73 | 12688.18 | -9042.55
160 | 14 | Inventory Visibility | 2025-09-01 | 19188.63 | 16873.79 | -2314.84
161 | 14 | Inventory Visibility | 2025-10-01 | 21949.38 | 16643.39 | -5305.99
162 | 14 | Inventory Visibility | 2025-11-01 | 20745.54 | 17257.48 | -3488.06
163 | 14 | Inventory Visibility | 2025-12-01 | 20122.53 | 14249.06 | -5873.47
164 | 14 | Inventory Visibility | 2026-01-01 | 19737.54 | 18496.21 | -1241.33
165 | 14 | Inventory Visibility | 2026-02-01 | 20053.39 | 10321.58 | -9731.81
166 | 14 | Inventory Visibility | 2026-03-01 | 21550.67 | 12712.13 | -8838.54
167 | 14 | Inventory Visibility | 2026-04-01 | 20550.03 | 17910.31 | -2639.72
168 | 14 | Inventory Visibility | 2026-05-01 | 21264.8 | 9964.18 | -11300.62
169 | 15 | Patient Scheduling Pilot | 2025-06-01 | 13040.3 | 15250.49 | 2210.19
170 | 15 | Patient Scheduling Pilot | 2025-07-01 | 12935.25 | 12982.44 | 47.19
171 | 15 | Patient Scheduling Pilot | 2025-08-01 | 12534.7 | 15595.52 | 3060.82
172 | 15 | Patient Scheduling Pilot | 2025-09-01 | 11639.16 | 9008.97 | -2630.19
173 | 15 | Patient Scheduling Pilot | 2025-10-01 | 12176.61 | 11959.52 | -217.09
174 | 15 | Patient Scheduling Pilot | 2025-11-01 | 12303.3 | 16922.57 | 4619.27
175 | 15 | Patient Scheduling Pilot | 2025-12-01 | 13044.75 | 16720.12 | 3675.37
176 | 15 | Patient Scheduling Pilot | 2026-01-01 | 12368.14 | 17265.69 | 4897.55
177 | 15 | Patient Scheduling Pilot | 2026-02-01 | 12286.53 | 12845.53 | 559
178 | 15 | Patient Scheduling Pilot | 2026-03-01 | 11574.19 | 14530.09 | 2955.9
179 | 15 | Patient Scheduling Pilot | 2026-04-01 | 13345.04 | 17183.51 | 3838.47
180 | 15 | Patient Scheduling Pilot | 2026-05-01 | 11801.9 | 12099.07 | 297.17
181 | 16 | Field Service Rollout | 2025-06-01 | 35077.35 | 33286.93 | -1790.42
182 | 16 | Field Service Rollout | 2025-07-01 | 35467.78 | 33331.51 | -2136.27
183 | 16 | Field Service Rollout | 2025-08-01 | 33922.14 | 29844.78 | -4077.36
184 | 16 | Field Service Rollout | 2025-09-01 | 31449.93 | 31323.32 | -126.61
185 | 16 | Field Service Rollout | 2025-10-01 | 32821 | 33189.22 | 368.22
186 | 16 | Field Service Rollout | 2025-11-01 | 34100.69 | 22528.13 | -11572.56
187 | 16 | Field Service Rollout | 2025-12-01 | 35400.43 | 31515.4 | -3885.03
188 | 16 | Field Service Rollout | 2026-01-01 | 33996.58 | 27951.29 | -6045.29
189 | 16 | Field Service Rollout | 2026-02-01 | 33963.67 | 31279.65 | -2684.02
190 | 16 | Field Service Rollout | 2026-03-01 | 33024.77 | 28351.27 | -4673.5
191 | 16 | Field Service Rollout | 2026-04-01 | 32508 | 20493.42 | -12014.58
192 | 16 | Field Service Rollout | 2026-05-01 | 34996.43 | 21080.31 | -13916.12
193 | 17 | Marketing Ops Migration | 2025-06-01 | 6496.76 | 5831.98 | -664.78
194 | 17 | Marketing Ops Migration | 2025-07-01 | 6811.4 | 6235.62 | -575.78
195 | 17 | Marketing Ops Migration | 2025-08-01 | 6158.32 | 3189.66 | -2968.66
196 | 17 | Marketing Ops Migration | 2025-09-01 | 7083.01 | 4922.18 | -2160.83
197 | 17 | Marketing Ops Migration | 2025-10-01 | 6709.26 | 4358.48 | -2350.78
198 | 17 | Marketing Ops Migration | 2025-11-01 | 6409.27 | 5615.89 | -793.38
199 | 17 | Marketing Ops Migration | 2025-12-01 | 7021.04 | 6231.42 | -789.62
200 | 17 | Marketing Ops Migration | 2026-01-01 | 6457.54 | 4857.32 | -1600.22
201 | 17 | Marketing Ops Migration | 2026-02-01 | 6584.26 | 4935.01 | -1649.25
202 | 17 | Marketing Ops Migration | 2026-03-01 | 6672.29 | 3684.59 | -2987.7
203 | 17 | Marketing Ops Migration | 2026-04-01 | 6914.12 | 4823.68 | -2090.44
204 | 17 | Marketing Ops Migration | 2026-05-01 | 7031.02 | 4061.25 | -2969.77
205 | 18 | Vendor Risk Program | 2025-06-01 | 22291.8 | 17140.88 | -5150.92
206 | 18 | Vendor Risk Program | 2025-07-01 | 21385.07 | 11910.88 | -9474.19
207 | 18 | Vendor Risk Program | 2025-08-01 | 21981.65 | 20535.81 | -1445.84
208 | 18 | Vendor Risk Program | 2025-09-01 | 19946.13 | 23054.57 | 3108.44
209 | 18 | Vendor Risk Program | 2025-10-01 | 20164.01 | 16339.9 | -3824.11
210 | 18 | Vendor Risk Program | 2025-11-01 | 21389.74 | 18026.02 | -3363.72
211 | 18 | Vendor Risk Program | 2025-12-01 | 21883.6 | 10294.26 | -11589.34
212 | 18 | Vendor Risk Program | 2026-01-01 | 21075.89 | 14843.81 | -6232.08
213 | 18 | Vendor Risk Program | 2026-02-01 | 19633.24 | 13441.42 | -6191.82
214 | 18 | Vendor Risk Program | 2026-03-01 | 20425.55 | 20388.57 | -36.98
215 | 18 | Vendor Risk Program | 2026-04-01 | 21625.04 | 18150.86 | -3474.18
216 | 18 | Vendor Risk Program | 2026-05-01 | 19517.42 | 19964.5 | 447.08
217 | 19 | Service Desk Re-platform | 2025-06-01 | 16407.34 | 6909.56 | -9497.78
218 | 19 | Service Desk Re-platform | 2025-07-01 | 16823.92 | 11205.28 | -5618.64
219 | 19 | Service Desk Re-platform | 2025-08-01 | 17410.2 | 8828.39 | -8581.81
220 | 19 | Service Desk Re-platform | 2025-09-01 | 17658.71 | 6572.33 | -11086.38
221 | 19 | Service Desk Re-platform | 2025-10-01 | 16891.48 | 8618.6 | -8272.88
222 | 19 | Service Desk Re-platform | 2025-11-01 | 17030.56 | 8518.62 | -8511.94
223 | 19 | Service Desk Re-platform | 2025-12-01 | 17990.7 | 6174.24 | -11816.46
224 | 19 | Service Desk Re-platform | 2026-01-01 | 17170.71 | 8612.7 | -8558.01
225 | 19 | Service Desk Re-platform | 2026-02-01 | 17860.85 | 6451.45 | -11409.4
226 | 19 | Service Desk Re-platform | 2026-03-01 | 17284.58 | 7072.51 | -10212.07
227 | 19 | Service Desk Re-platform | 2026-04-01 | 16445.13 | 6070.32 | -10374.81
228 | 19 | Service Desk Re-platform | 2026-05-01 | 15767.58 | 10459.56 | -5308.02
229 | 20 | Quality Management Rollout | 2025-06-01 | 5281.85 | 4232.77 | -1049.08
230 | 20 | Quality Management Rollout | 2025-07-01 | 4688.27 | 4140.03 | -548.24
231 | 20 | Quality Management Rollout | 2025-08-01 | 4895.67 | 5889.41 | 993.74
232 | 20 | Quality Management Rollout | 2025-09-01 | 4831.67 | 4330.19 | -501.48
233 | 20 | Quality Management Rollout | 2025-10-01 | 5018.22 | 4384.89 | -633.33
234 | 20 | Quality Management Rollout | 2025-11-01 | 4694.19 | 4951.64 | 257.45
235 | 20 | Quality Management Rollout | 2025-12-01 | 4843.94 | 4132.22 | -711.72
236 | 20 | Quality Management Rollout | 2026-01-01 | 4899.57 | 2682.77 | -2216.8
237 | 20 | Quality Management Rollout | 2026-02-01 | 4835.19 | 3108.64 | -1726.55
238 | 20 | Quality Management Rollout | 2026-03-01 | 4622.38 | 4487.34 | -135.04
239 | 20 | Quality Management Rollout | 2026-04-01 | 4714.3 | 5730.57 | 1016.27
240 | 20 | Quality Management Rollout | 2026-05-01 | 5227.03 | 2978.13 | -2248.9

## Dashboard
Project Portfolio — Health Dashboard
As of: | 2026-05-02
Synthetic data ¦ Built with Excel + SQL
TOTAL PROJECTS |  | ON TRACK |  | AT RISK | OVER BUDGET |  | OVERDUE TASKS
20 |  | 11 |  | 5 | 4 |  | 245
Project Health Summary
Health | # Projects | % of Portfolio
On Track | 11 | 55%
At Risk | 5 | 25%
Over Budget | 4 | 20%
Top 5 Over-Budget Projects
Project | Client | Budget | Actual | Overrun |  | Month | Planned | Actual
Cybersecurity Uplift | Acme Co. | 400000 | 448485.6 | 48485.6 |  | 2025-06-01 | 316596.9 | 232791.02
Patient Scheduling Pilot | Umbrella Bio | 150000 | 172363.52 | 22363.52 |  | 2025-07-01 | 318655.51 | 223739.36
Compliance Remediation | Initech | 120000 | 134103.24 | 14103.24 |  | 2025-08-01 | 317824.96 | 237730.05
ERP Implementation | Acme Co. | 60000 | 70571.26 | 10571.26 |  | 2025-09-01 | 311002.97 | 246632.42
[6 empty] | 2025-10-01 | 304867.78 | 252939.9
[6 empty] | 2025-11-01 | 315279.41 | 239124.15
[6 empty] | 2025-12-01 | 317134.37 | 238608.19
Monthly Spend — Planned vs Actual | [5 empty] | 2026-01-01 | 310567.4 | 263791.38
[6 empty] | 2026-02-01 | 316348.69 | 227558.44
[6 empty] | 2026-03-01 | 312110.86 | 231435.61
[6 empty] | 2026-04-01 | 309765.78 | 259467.29
[6 empty] | 2026-05-01 | 313370.87 | 225552.74
Capacity Hot List — Overallocated Employees (any week >45 hrs)
Employee | Department | # Weeks Overallocated
Hailey Diaz | Operations | 4
Sam Bell | Finance | 3
Paige Cook | Design | 3
Owen Murphy | Operations | 3
Nina Morris | Engineering | 3
Jade Edwards | Engineering | 3
Caleb Carter | Finance | 3
Aiden Hill | PMO | 3
Victor Wright | Operations | 3
Sofia Young | PMO | 3
(helper) | employee_id | name | dept | overalloc_wks
| 1 | Alex Johnson | Delivery | 1e-06
| 2 | Brystal Patel | Operations | 2
| 3 | Carlos Garcia | Finance | 2
| 4 | Dana Lee | Operations | 1
| 5 | Eli Nguyen | Finance | 5e-06
| 6 | Fatima Brown | Operations | 1
| 7 | Grace Khan | Operations | 2
| 8 | Hassan Davis | Operations | 2
| 9 | Imani Martin | Delivery | 3
| 10 | Jorge Wilson | Finance | 1
| 11 | Kelly Anderson | Finance | 1
| 12 | Liam Thomas | Finance | 1.2e-05
| 13 | Maya Jackson | PMO | 3
| 14 | Noah White | Delivery | 1
| 15 | Olivia Harris | Engineering | 2
| 16 | Priya Clark | Engineering | 1.6e-05
| 17 | Quinn Lewis | Finance | 1
| 18 | Ravi Walker | Operations | 1
| 19 | Sofia Young | PMO | 3
| 20 | Theo Allen | Delivery | 1
| 21 | Uma King | Delivery | 2
| 22 | Victor Wright | Operations | 3
| 23 | Wendy Scott | Operations | 1
| 24 | Xavier Green | PMO | 2
| 25 | Yara Baker | Engineering | 1
| 26 | Zane Adams | Delivery | 2
| 27 | Aiden Hill | PMO | 3
| 28 | Bella Mitchell | Design | 2
| 29 | Caleb Carter | Finance | 3
| 30 | Diana Roberts | PMO | 1
| 31 | Ethan Phillips | Delivery | 2
| 32 | Fiona Evans | Delivery | 3.2e-05
| 33 | Gavin Turner | Finance | 2
| 34 | Hailey Diaz | Operations | 4
| 35 | Ian Parker | Finance | 2
| 36 | Jade Edwards | Engineering | 3
| 37 | Kyle Collins | Delivery | 1
| 38 | Lena Reyes | Delivery | 1
| 39 | Marcus Stewart | Operations | 2
| 40 | Nina Morris | Engineering | 3
| 41 | Owen Murphy | Operations | 3
| 42 | Paige Cook | Design | 3
| 43 | Quincy Rogers | Finance | 2
| 44 | Rachel Morgan | Delivery | 1
| 45 | Sam Bell | Finance | 3
| 46 | Tara Cooper | Operations | 4.6e-05
| 47 | Umar Bailey | Delivery | 2
| 48 | Vera Cox | Operations | 1
| 49 | Will Howard | Operations | 4.9e-05
| 50 | Zoe Smith | Delivery | 5e-05

## Exec_OnePager
Project Portfolio Health — Executive Summary
Synthetic dataset ¦ Sample portfolio piece
PROJECTS | % ON TRACK | % OVER BUDGET | TOTAL OVERRUN
20 | 55% | 20% | 95523.62
What this dashboard shows
• Single weekly view of project health across all 20 projects.
• Health flag is automatic: 'Over Budget' when actuals exceed plan; 'At Risk' when
budget burn is running >15 percentage points ahead of % complete.
• Capacity hot list flags employees logging >45 hours for any week in the last 8.
Recommended actions
1. Re-baseline the over-budget projects with the COO this week.
2. Open weekly check-in on any project where (% burned − % complete) > 15.
3. Redistribute work from overallocated staff before quality slips.
4. Replace ad-hoc PM emails with this dashboard, refreshed every Monday.
Built by Brystal ¦ Excel + SQL portfolio piece